## Tasks
Lukas Vogel
Task ID | Task Name | Parent ID | Parent Name | Parent URL | Assignee | TX URL (url) | Sent Tokens (currency) | Bounty (formula) | Time Estimate | Time Logged | Urgency (1-5) (number) | Importance (1-5) (number) | Priority | Status
3gn1crf | Onboarding People & Organizational Work |  |  |  | Lukas Vogel |  |  | 422.2644 | 48h | 48h 1m | 4 | 5 | URGENT | CLOSED
Mike Sinn | [6 empty] | Total: | 422.2644
Task ID | Task Name | Parent ID | Parent Name | Parent URL | Assignee | TX URL (url) | Sent Tokens (currency) | Bounty (formula) | Time Estimate | Time Logged | Urgency (1-5) (number) | Importance (1-5) (number) | Priority | Status
2tt0rjr | How much would it cost to improve UI for a B2C product vs B2B product? |  |  |  | Mike Sinn |  |  | 45.9816 | 30m |  | 5 | 5 | URGENT | CLOSED
2t2t1xf | The CureDAO Show Starring Ali Jorani! |  |  |  | Mike Sinn |  |  | 36.4021 | 30m |  | 4 | 5 | URGENT | CLOSED
2t8eff3 | The CureDAO Show Starring Dmitri! |  |  |  | Mike Sinn |  |  | 36.4021 | 30m |  | 4 | 5 | URGENT | CLOSED
2tec294 | The CureDAO Show Starring Jon Fryer! |  |  |  | Mike Sinn |  |  | 36.4021 | 30m |  | 4 | 5 | URGENT | CLOSED
Andreas Melhede | [6 empty] | Total: | 155.1879
Task ID | Task Name | Parent ID | Parent Name | Parent URL | Assignee | TX URL (url) | Sent Tokens (currency) | Bounty (formula) | Time Estimate | Time Logged | Urgency (1-5) (number) | Importance (1-5) (number) | Priority | Status
3d899ye | Compensate people with tokens |  |  |  | Andreas Melhede |  |  | 96.5614 | 1h 3m | 1h 4m | 5 | 5 | URGENT | CLOSED
3gn15p2 | Check on deadlines for tasks |  |  |  | Andreas Melhede |  |  | 1.5327 | 1m | 1m | 5 | 5 | URGENT | CLOSED
3gn4kkb | Check on deadlines for tasks |  |  |  | Andreas Melhede |  |  | 1.5327 | 1m | 1m | 5 | 5 | URGENT | CLOSED
3gut974 | Check on deadlines for tasks |  |  |  | Andreas Melhede |  |  | 116.4867 | 1h 16m | 1h 17m | 5 | 5 | URGENT | CLOSED
3h0erqk | Check on deadlines for tasks |  |  |  | Andreas Melhede |  |  | 4.5982 | 3m | 3m | 5 | 5 | URGENT | CLOSED
2hq48j1 | Apply at SuperDAO |  |  |  | Andreas Melhede |  |  | 27.589 | 18m | 18m | 5 | 5 | URGENT | CLOSED
3h63c73 | Check on deadlines for tasks |  |  |  | Andreas Melhede |  |  | 3.0654 | 2m | 2m | 5 | 5 | URGENT | CLOSED
3h68wuc | Check on deadlines for tasks |  |  |  | Andreas Melhede |  |  | 1.5327 | 1m | 1m | 5 | 5 | URGENT | CLOSED
2tm5a2c | Send 10 $CURE1 Tokens & let them know | 2tm5a2b | Tom-Gøran Skog | https://app.clickup.com/t/2tm5a2b | Andreas Melhede |  |  | 0 | [5 empty] | CLOSED
3hbxgm0 | Check on deadlines for tasks |  |  |  | Andreas Melhede |  |  | 3.0654 | 2m | 2m | 5 | 5 | URGENT | CLOSED
3gn1crf | Onboarding People & Organizational Work |  |  |  | Andreas Melhede |  |  | 3072.3372 |  |  | 4 | 5 | URGENT | CLOSED
Ali Jorani | [6 empty] | Total: | 3328.3015
Task ID | Task Name | Parent ID | Parent Name | Parent URL | Assignee | TX URL (url) | Sent Tokens (currency) | Bounty (formula) | Time Estimate | Time Logged | Urgency (1-5) (number) | Importance (1-5) (number) | Priority | Status
3gmyfbx | Onboarding Task |  |  |  | Ali Jorani | [7 empty] | HIGH | COMPLETE
3gmyfby | Organizing with the Hierarchy | 3gmyfbx | Onboarding Task | https://app.clickup.com/t/3gmyfbx | Ali Jorani |  |  | 1.3411 | 3m |  | 2 | 4 | NORMAL | COMPLETE
3gmyfbz | Filter and sort your tasks | 3gmyfbx | Onboarding Task | https://app.clickup.com/t/3gmyfbx | Ali Jorani |  |  | 1.3411 | 3m |  | 2 | 4 | NORMAL | COMPLETE
3gmyfc0 | Task Statuses and Priorities | 3gmyfbx | Onboarding Task | https://app.clickup.com/t/3gmyfbx | Ali Jorani |  |  | 2.6823 | 3m |  | 3 | 5 | HIGH | COMPLETE
3gmyfc1 | Setting due dates to keep your team on track | 3gmyfbx | Onboarding Task | https://app.clickup.com/t/3gmyfbx | Ali Jorani |  |  | 4.4704 | 5m |  | 3 | 5 | URGENT | COMPLETE
3gmyfc2 | Home and Prioritizing your team's tasks | 3gmyfbx | Onboarding Task | https://app.clickup.com/t/3gmyfbx | Ali Jorani |  |  | 3.5763 | 4m |  | 3 | 5 | HIGH | COMPLETE
3gmyfc3 | Collaborating with tasks | 3gmyfbx | Onboarding Task | https://app.clickup.com/t/3gmyfbx | Ali Jorani |  |  | 0.63863 | 5m |  | 1 | 3 | LOW | COMPLETE
3gmyfc4 | Recurring tasks: this task will restart when closed | 3gmyfbx | Onboarding Task | https://app.clickup.com/t/3gmyfbx | Ali Jorani |  |  | 0.89409 | 2m |  | 2 | 4 | NORMAL | COMPLETE
3gmyfc5 | Managing ClickUp Notifications | 3gmyfbx | Onboarding Task | https://app.clickup.com/t/3gmyfbx | Ali Jorani |  |  | 1.3411 | 3m |  | 2 | 4 | HIGH | COMPLETE
3gmyfc6 | Communication with your team in ClickUp | 3gmyfbx | Onboarding Task | https://app.clickup.com/t/3gmyfbx | Ali Jorani |  |  | 1.7882 | 4m |  | 2 | 4 | LOW | COMPLETE
3gmyfc7 | Weekly Team Goals | 3gmyfbx | Onboarding Task | https://app.clickup.com/t/3gmyfbx | Ali Jorani |  |  | 0.38318 | 3m |  | 1 | 3 | LOW | COMPLETE
3gmyfc8 | Save your team time with reusable templates! | 3gmyfbx | Onboarding Task | https://app.clickup.com/t/3gmyfbx | Ali Jorani |  |  | 2.6823 | 3m |  | 3 | 5 | HIGH | COMPLETE
3gmyfc9 | Custom Fields | 3gmyfbx | Onboarding Task | https://app.clickup.com/t/3gmyfbx | Ali Jorani |  |  | 2.6823 | 6m |  | 2 | 4 | NORMAL | COMPLETE
3gmyfca | Dashboards at a high level to measure your team's progress | 3gmyfbx | Onboarding Task | https://app.clickup.com/t/3gmyfbx | Ali Jorani |  |  | 2.6823 | 6m |  | 2 | 4 | NORMAL | COMPLETE
3gmyfcb | Disable Hot Keys for Better Linking to Documents | 3gmyfbx | Onboarding Task | https://app.clickup.com/t/3gmyfbx | Ali Jorani |  |  | 1.3411 | 3m |  | 2 | 4 | NORMAL | COMPLETE
3gmyfcc | ClickUp Views | 3gmyfbx | Onboarding Task | https://app.clickup.com/t/3gmyfbx | Ali Jorani |  |  | 0.51091 | 4m |  | 1 | 3 | LOW | COMPLETE
3gmyfcd | The ClickUp Chrome Extension | 3gmyfbx | Onboarding Task | https://app.clickup.com/t/3gmyfbx | Ali Jorani |  |  | 1.7882 | 4m |  | 2 | 4 | NORMAL | COMPLETE
3gmyfce | How to make social media posts for CureDAO | 3gmyfbx | Onboarding Task | https://app.clickup.com/t/3gmyfbx | Ali Jorani |  |  | 1.3411 | 3m |  | 2 | 4 | NORMAL | COMPLETE
3gmyfcg | How To Reduce Discord Notifications | 3gmyfbx | Onboarding Task | https://app.clickup.com/t/3gmyfbx | Ali Jorani |  |  | 1.3411 | 3m |  | 2 | 4 | NORMAL | COMPLETE
3gmyfch | Add CureDAO's Calendar to Google Calendar | 3gmyfbx | Onboarding Task | https://app.clickup.com/t/3gmyfbx | Ali Jorani |  |  | 0.89409 | 1m |  | 3 | 5 | HIGH | COMPLETE
3gmyfcj | Add PCUREDAO to MetaMask | 3gmyfbx | Onboarding Task | https://app.clickup.com/t/3gmyfbx | Ali Jorani |  |  | 7.1527 | 8m |  | 3 | 5 | HIGH | COMPLETE
3gmyfck | Go through our Litepaper, and schedule a call to find your first quest and get started! | 3gmyfbx | Onboarding Task | https://app.clickup.com/t/3gmyfbx | Ali Jorani |  |  | 20.6279 | 17m |  | 4 | 5 | URGENT | COMPLETE
3gmyfcm | Do this last: How would you improve the onboarding process? | 3gmyfbx | Onboarding Task | https://app.clickup.com/t/3gmyfbx | Ali Jorani |  |  | 6.067 | 5m |  | 4 | 5 | HIGH | COMPLETE
[7 empty] | Total: | 67.5674