## Tasks
Lukas Vogel
Task ID | Task Name | Parent ID | Parent Name | Parent URL | Assignee | TX URL (url) | Sent Tokens (currency) | Bounty (formula) | Time Estimate | Time Logged | Urgency (1-5) (number) | Importance (1-5) (number) | Priority | Status
3c623uf | Onboarding People & Organizational Work |  |  |  | Lukas Vogel |  |  | 311.8751 | 31h 38m | 31h 38m | 4 | 5 | URGENT | CLOSED
Mike Sinn | [6 empty] | Total: | 311.8751
Task ID | Task Name | Parent ID | Parent Name | Parent URL | Assignee | TX URL (url) | Sent Tokens (currency) | Bounty (formula) | Time Estimate | Time Logged | Urgency (1-5) (number) | Importance (1-5) (number) | Priority | Status
2mtfymh | Setting Up CureDAO Wiki at https://wiki.curedao.org/ |  |  |  | Mike Sinn |  |  | 701.9858 | 7h 38m | 7h 39m | 5 | 5 | URGENT | CLOSED
2r0hyzu | The CureDAO Show Starring Rachel Strohmeyer! |  |  |  | Mike Sinn |  |  | 36.4021 | 30m |  | 4 | 5 | URGENT | CLOSED
3tp1kt9 | The CureDAO Show Starring Hampton Black! |  |  |  | Mike Sinn |  |  | 36.4021 | 30m |  | 4 | 5 | URGENT | CLOSED
3u1cmj3 | Reputable Weekly Sync |  |  |  | Mike Sinn |  |  | 60.6702 | 50m |  | 4 | 5 | URGENT | CLOSED
Luís Pinto | [6 empty] | Total: | 835.4601
Task ID | Task Name | Parent ID | Parent Name | Parent URL | Assignee | TX URL (url) | Sent Tokens (currency) | Bounty (formula) | Time Estimate | Time Logged | Urgency (1-5) (number) | Importance (1-5) (number) | Priority | Status
39nxyk1 | Organizing with the Hierarchy | 39nxyk0 | Onboarding Task | https://app.clickup.com/t/39nxyk0 | Luís Pinto |  |  | 1.3411 | 3m |  | 2 | 4 | NORMAL | COMPLETE
39nxyk2 | Filter and sort your tasks | 39nxyk0 | Onboarding Task | https://app.clickup.com/t/39nxyk0 | Luís Pinto |  |  | 1.3411 | 3m |  | 2 | 4 | NORMAL | COMPLETE
39nxyk3 | Task Statuses and Priorities | 39nxyk0 | Onboarding Task | https://app.clickup.com/t/39nxyk0 | Luís Pinto |  |  | 2.6823 | 3m |  | 3 | 5 | HIGH | COMPLETE
39nxyk4 | Setting due dates to keep your team on track | 39nxyk0 | Onboarding Task | https://app.clickup.com/t/39nxyk0 | Luís Pinto |  |  | 6.2586 | 7m |  | 3 | 5 | URGENT | COMPLETE
39nxyk6 | Home and Prioritizing your team's tasks | 39nxyk0 | Onboarding Task | https://app.clickup.com/t/39nxyk0 | Luís Pinto |  |  | 4.4704 | 5m |  | 3 | 5 | HIGH | COMPLETE
39nxyk7 | Collaborating with tasks | 39nxyk0 | Onboarding Task | https://app.clickup.com/t/39nxyk0 | Luís Pinto |  |  | 0.63863 | 5m |  | 1 | 3 | LOW | COMPLETE
39nxyka | Recurring tasks: this task will restart when closed | 39nxyk0 | Onboarding Task | https://app.clickup.com/t/39nxyk0 | Luís Pinto |  |  | 0.89409 | 2m |  | 2 | 4 | NORMAL | COMPLETE
39nxykd | Managing ClickUp Notifications | 39nxyk0 | Onboarding Task | https://app.clickup.com/t/39nxyk0 | Luís Pinto |  |  | 1.3411 | 3m |  | 2 | 4 | HIGH | COMPLETE
39nxykg | Communication with your team in ClickUp | 39nxyk0 | Onboarding Task | https://app.clickup.com/t/39nxyk0 | Luís Pinto |  |  | 2.2352 | 5m |  | 2 | 4 | LOW | COMPLETE
39nxykk | Weekly Team Goals | 39nxyk0 | Onboarding Task | https://app.clickup.com/t/39nxyk0 | Luís Pinto |  |  | 0.38318 | 3m |  | 1 | 3 | LOW | COMPLETE
39nxykn | Save your team time with reusable templates! | 39nxyk0 | Onboarding Task | https://app.clickup.com/t/39nxyk0 | Luís Pinto |  |  | 2.6823 | 3m |  | 3 | 5 | HIGH | COMPLETE
39nxykp | Custom Fields | 39nxyk0 | Onboarding Task | https://app.clickup.com/t/39nxyk0 | Luís Pinto |  |  | 3.1293 | 7m |  | 2 | 4 | NORMAL | COMPLETE
39nxykr | Dashboards at a high level to measure your team's progress | 39nxyk0 | Onboarding Task | https://app.clickup.com/t/39nxyk0 | Luís Pinto |  |  | 3.1293 | 7m |  | 2 | 4 | NORMAL | COMPLETE
39nxyku | Disable Hot Keys for Better Linking to Documents | 39nxyk0 | Onboarding Task | https://app.clickup.com/t/39nxyk0 | Luís Pinto |  |  | 1.3411 | 3m |  | 2 | 4 | NORMAL | COMPLETE
39nxyky | ClickUp Views | 39nxyk0 | Onboarding Task | https://app.clickup.com/t/39nxyk0 | Luís Pinto |  |  | 0.63863 | 5m |  | 1 | 3 | LOW | COMPLETE
39nxykz | The ClickUp Chrome Extension | 39nxyk0 | Onboarding Task | https://app.clickup.com/t/39nxyk0 | Luís Pinto |  |  | 2.2352 | 5m |  | 2 | 4 | NORMAL | COMPLETE
39nxym2 | How to make social media posts for CureDAO | 39nxyk0 | Onboarding Task | https://app.clickup.com/t/39nxyk0 | Luís Pinto |  |  | 1.3411 | 3m |  | 2 | 4 | NORMAL | COMPLETE
39nxym3 | How To Reduce Discord Notifications | 39nxyk0 | Onboarding Task | https://app.clickup.com/t/39nxyk0 | Luís Pinto |  |  | 1.3411 | 3m |  | 2 | 4 | NORMAL | COMPLETE
39nxym5 | Add CureDAO's Calendar to Google Calendar | 39nxyk0 | Onboarding Task | https://app.clickup.com/t/39nxyk0 | Luís Pinto |  |  | 0.89409 | 1m |  | 3 | 5 | HIGH | COMPLETE
39nxym8 | Add GCURES to MetaMask | 39nxyk0 | Onboarding Task | https://app.clickup.com/t/39nxyk0 | Luís Pinto |  |  | 8.9409 | 10m |  | 3 | 5 | HIGH | COMPLETE
39nxyma | Schedule a call to find your first quest and get started! | 39nxyk0 | Onboarding Task | https://app.clickup.com/t/39nxyk0 | Luís Pinto |  |  | 3.6402 | 3m |  | 4 | 5 | URGENT | COMPLETE
39nxymb | Do this last: How would you improve the onboarding process? | 39nxyk0 | Onboarding Task | https://app.clickup.com/t/39nxyk0 | Luís Pinto |  |  | 10.9206 | 9m |  | 4 | 5 | HIGH | COMPLETE
Andreas Melhede | [6 empty] | Total: | 61.8197
Task ID | Task Name | Parent ID | Parent Name | Parent URL | Assignee | TX URL (url) | Sent Tokens (currency) | Bounty (formula) | Time Estimate | Time Logged | Urgency (1-5) (number) | Importance (1-5) (number) | Priority | Status
3bf79ak | Compensate people with tokens |  |  |  | Andreas Melhede |  |  | 162.4683 | 1h 46m | 1h 47m | 5 | 5 | URGENT | CLOSED
3c623nz | Check on deadlines for tasks |  |  |  | Andreas Melhede |  |  | 10.729 | 7m | 7m | 5 | 5 | URGENT | CLOSED
2rd3yud | Send 10 $CURE1 Tokens & let them know | 2rd3yu7 | Aaron | https://app.clickup.com/t/2rd3yu7 | Andreas Melhede |  |  | 0 | [5 empty] | CLOSED
2rd3yv1 | Add to Clickup, make them guests, create onboarding tasks for them, and grant them access to their onboarding tasks | 2rd3yu7 | Aaron | https://app.clickup.com/t/2rd3yu7 | Andreas Melhede |  |  | 0 | [5 empty] | CLOSED
3cbqvje | Send 10 $CURE1 Tokens & let them know | 3cbqvjd | Kayiranga Eric | https://app.clickup.com/t/3cbqvjd | Andreas Melhede |  |  | 0 | [5 empty] | CLOSED
3ch9azh | Check on deadlines for tasks |  |  |  | Andreas Melhede |  |  | 29.1217 | 19m | 20m | 5 | 5 | URGENT | CLOSED
2rjr7cd | Send 10 $CURE1 Tokens & let them know | 2rjr7c9 | Emjay Famyfuerza | https://app.clickup.com/t/2rjr7c9 | Andreas Melhede |  |  | 0 | [5 empty] | CLOSED
2rjr7cm | Add to Clickup, make them guests, create onboarding tasks for them, and grant them access to their onboarding tasks | 2rjr7c9 | Emjay Famyfuerza | https://app.clickup.com/t/2rjr7c9 | Andreas Melhede |  |  | 0 | [5 empty] | CLOSED
39g3ffr | Send 10 $CURE1 Tokens & let them know | 39g3ffq | Luís Pinto | https://app.clickup.com/t/39g3ffq | Andreas Melhede |  |  | 0 | [5 empty] | CLOSED
2r675pv | Send 10 $CURE1 Tokens & let them know | 2r675pu | Arun Chauhan | https://app.clickup.com/t/2r675pu | Andreas Melhede |  |  | 0 | [5 empty] | CLOSED
2r675pz | Add to Clickup, make them guests, create onboarding tasks for them, and grant them access to their onboarding tasks | 2r675pu | Arun Chauhan | https://app.clickup.com/t/2r675pu | Andreas Melhede |  |  | 0 | [5 empty] | CLOSED
3cq1wjh | Check on deadlines for tasks |  |  |  | Andreas Melhede |  |  | 3.0654 | 2m | 3m | 5 | 5 | URGENT | CLOSED
3cwu5yh | Check on deadlines for tasks |  |  |  | Andreas Melhede |  |  | 29.1217 | 19m | 20m | 5 | 5 | URGENT | CLOSED
2rbvk68 | No Feeback from my side as of now |  |  |  | Andreas Melhede |  |  | 0 | [5 empty] | CLOSED
3d2er3w | Check on deadlines for tasks |  |  |  | Andreas Melhede |  |  | 6.1309 | 4m | 5m | 5 | 5 | URGENT | CLOSED
3d2m6uh | Prepare for Gitcoin Round |  |  |  | Andreas Melhede |  |  | 99.6268 | 1h 5m | 1h 6m | 5 | 5 | URGENT | CLOSED
2w4zjug | Send 10 $CURE1 Tokens & let them know | 2w4zjue | Omar ElNaggar | https://app.clickup.com/t/2w4zjue | Andreas Melhede |  |  | 0 | [5 empty] | CLOSED
3c623uf | Onboarding People & Organizational Work |  |  |  | Andreas Melhede |  |  | 1991.4047 | 31h 38m | 31h 38m | 4 | 5 | URGENT | CLOSED
[7 empty] | Total: | 2331.6686