## Tasks
Mike Sinn, Andreas Melhede
Task ID | Task Name | Parent ID | Parent Name | Parent URL | Assignee | Bounty (formula) | TX URL (url) | Sent Tokens (currency) | Time Estimate | Time Logged | Urgency (1-5) (number) | Importance (1-5) (number) | Priority | Status
2px3j4h | Apply at alliance.xyz and create company FAQ |  |  |  | Mike Sinn, Andreas Melhede | 314.2076 |  |  | 3h 25m | 3h 24m | 5 | 5 | URGENT | SENT
2pwz06w | Create Optomitron Project on Website |  |  |  | Mike Sinn, Andreas Melhede | 291.2168 |  |  | 4h | 1h 8m | 4 | 5 |  | COMPLETE
Wouter van der Linden
Task ID | Task Name | Parent ID | Parent Name | Parent URL | Assignee | Bounty (formula) | TX URL (url) | Sent Tokens (currency) | Time Estimate | Time Logged | Urgency (1-5) (number) | Importance (1-5) (number) | Priority | Status
25mabgn | Setting due dates to keep your team on track |  |  |  | Wouter van der Linden | 2.6823 |  |  | 3m |  | 3 | 5 | HIGH | CLOSED
25mabh6 | Home and Prioritizing your team's tasks |  |  |  | Wouter van der Linden | 2.6823 |  |  | 3m |  | 3 | 5 | HIGH | CLOSED
25mabgu | Save your team time with reusable templates! |  |  |  | Wouter van der Linden | 2.6823 |  |  | 3m |  | 3 | 5 | HIGH | CLOSED
25mabj3 | Task Statuses and Priorities |  |  |  | Wouter van der Linden | 2.6823 |  |  | 3m |  | 3 | 5 | HIGH | CLOSED
25mabhe | Add $GCURES to MetaMask |  |  |  | Wouter van der Linden | 13.4113 |  |  | 15m |  | 3 | 5 | HIGH | CLOSED
25mabhx | How To Reduce Discord Notifications |  |  |  | Wouter van der Linden | 2.6823 |  |  | 3m |  | 3 | 5 | HIGH | CLOSED
25mabha | Easily Save Bookmarks to Lists with the ClickUp Chrome Extension |  |  |  | Wouter van der Linden | 2.1075 |  |  | 3m |  | 3 | 4 | NORMAL | CLOSED
25mabg5 | Filter and sort your tasks |  |  |  | Wouter van der Linden | 2.1075 |  |  | 3m |  | 3 | 4 | NORMAL | CLOSED
25mabgz | Collaborating with tasks |  |  |  | Wouter van der Linden | 2.1075 |  |  | 3m |  | 3 | 4 | NORMAL | CLOSED
25mabfr | Recurring tasks: this task will restart when closed |  |  |  | Wouter van der Linden | 2.1075 |  |  | 3m |  | 3 | 4 | NORMAL | CLOSED
25mabhg | Organizing with the Hierarchy |  |  |  | Wouter van der Linden | 2.1075 |  |  | 3m |  | 3 | 4 | NORMAL | CLOSED
25mabfz | Managing ClickUp Notifications |  |  |  | Wouter van der Linden | 2.1075 |  |  | 3m |  | 3 | 4 | NORMAL | CLOSED
25mabgx | Weekly Team Goals |  |  |  | Wouter van der Linden | 0.3832 |  |  | 3m |  | 1 | 3 | NORMAL | CLOSED
25mabhz | How to make social media posts |  |  |  | Wouter van der Linden | 2.1075 |  |  | 3m |  | 3 | 4 | NORMAL | CLOSED
25mabht | Custom Fields |  |  |  | Wouter van der Linden | 2.1075 |  |  | 3m |  | 3 | 4 | NORMAL | CLOSED
25mabhj | Dashboards at a high level to measure your team's progress |  |  |  | Wouter van der Linden | 2.1075 |  |  | 3m |  | 3 | 4 | NORMAL | CLOSED
25mabhc | Communication with your team in ClickUp |  |  |  | Wouter van der Linden | 0.1916 |  |  | 3m |  | 1 | 2 | LOW | CLOSED
25mabg8 | ClickUp Views |  |  |  | Wouter van der Linden | 0.3832 |  |  | 3m |  | 1 | 3 | LOW | CLOSED
Vincenzo Domina |  |  |  |  | Total: | 46.7483
Task ID | Task Name | Parent ID | Parent Name | Parent URL | Assignee | Bounty (formula) | TX URL (url) | Sent Tokens (currency) | Time Estimate | Time Logged | Urgency (1-5) (number) | Importance (1-5) (number) | Priority | Status
22hb71m | Add partner logos to new website |  |  |  | Vincenzo Domina | 42.1498 |  |  | 1h | 1h | 4 | 3 | URGENT | CLOSED
25zknfu | Do this last: How would you improve the onboarding process? |  |  |  | Vincenzo Domina | 12.134 |  |  | 10m |  | 4 | 5 | HIGH | CLOSED
25zknfr | Organizing with the Hierarchy |  |  |  | Vincenzo Domina | 1.7882 |  |  | 4m |  | 2 | 4 | NORMAL | CLOSED
25zknfv | Custom Fields |  |  |  | Vincenzo Domina | 2.6823 |  |  | 6m |  | 2 | 4 | NORMAL | CLOSED
25zknft | Dashboards at a high level to measure your team's progress |  |  |  | Vincenzo Domina | 2.2352 |  |  | 5m |  | 2 | 4 | NORMAL | CLOSED
25zknf9 | Disable Hot Keys for Better Linking to Documents |  |  |  | Vincenzo Domina | 1.3411 |  |  | 3m |  | 2 | 4 | NORMAL | CLOSED
25zknfk | Easily Save Bookmarks to Lists with the ClickUp Chrome Extension |  |  |  | Vincenzo Domina | 1.3411 |  |  | 3m |  | 2 | 4 | NORMAL | CLOSED
25zknfa | Setting due dates to keep your team on track |  |  |  | Vincenzo Domina | 2.2352 |  |  | 5m |  | 2 | 4 | NORMAL | CLOSED
25zknfw | How To Reduce Discord Notifications |  |  |  | Vincenzo Domina | 1.3411 |  |  | 3m |  | 2 | 4 | NORMAL | CLOSED
25zknfd | Weekly Team Goals |  |  |  | Vincenzo Domina | 0.3832 |  |  | 3m |  | 1 | 3 | NORMAL | CLOSED
25zknfp | Communication with your team in ClickUp |  |  |  | Vincenzo Domina | 0.1916 |  |  | 3m |  | 1 | 2 | LOW | CLOSED
25zknf7 | ClickUp Views |  |  |  | Vincenzo Domina | 0.5109 |  |  | 4m |  | 1 | 3 | LOW | CLOSED
Suporno Sarkar |  |  |  |  | Total: | 68.3337
Task ID | Task Name | Parent ID | Parent Name | Parent URL | Assignee | Bounty (formula) | TX URL (url) | Sent Tokens (currency) | Time Estimate | Time Logged | Urgency (1-5) (number) | Importance (1-5) (number) | Priority | Status
2khm9nt | Setting due dates to keep your team on track | 2khm9nr | Onboarding Task | https://app.clickup.com/t/2khm9nr | Suporno Sarkar | 4.4704 |  |  | 5m |  | 3 | 5 | URGENT | CLOSED
2khm9nv | Home and Prioritizing your team's tasks | 2khm9nr | Onboarding Task | https://app.clickup.com/t/2khm9nr | Suporno Sarkar | 2.6823 |  |  | 3m |  | 3 | 5 | HIGH | CLOSED
2khm9nw | Save your team time with reusable templates! | 2khm9nr | Onboarding Task | https://app.clickup.com/t/2khm9nr | Suporno Sarkar | 2.6823 |  |  | 3m |  | 3 | 5 | HIGH | CLOSED
2khm9nx | Task Statuses and Priorities | 2khm9nr | Onboarding Task | https://app.clickup.com/t/2khm9nr | Suporno Sarkar | 2.6823 |  |  | 3m |  | 3 | 5 | HIGH | CLOSED
2khm9ny | Add $GCURES to MetaMask | 2khm9nr | Onboarding Task | https://app.clickup.com/t/2khm9nr | Suporno Sarkar | 8.9409 |  |  | 10m |  | 3 | 5 | HIGH | CLOSED
2khm9p0 | Add CureDAO Calendar to Google Calendar | 2khm9nr | Onboarding Task | https://app.clickup.com/t/2khm9nr | Suporno Sarkar | 0.8941 |  |  | 1m |  | 3 | 5 | HIGH | CLOSED
2khm9p1 | Recurring tasks: this task will restart when closed | 2khm9nr | Onboarding Task | https://app.clickup.com/t/2khm9nr | Suporno Sarkar | 1.3411 |  |  | 3m |  | 2 | 4 | NORMAL | CLOSED
2khm9p4 | Filter and sort your tasks | 2khm9nr | Onboarding Task | https://app.clickup.com/t/2khm9nr | Suporno Sarkar | 1.3411 |  |  | 3m |  | 2 | 4 | NORMAL | CLOSED
2khm9p5 | Organizing with the Hierarchy | 2khm9nr | Onboarding Task | https://app.clickup.com/t/2khm9nr | Suporno Sarkar | 1.7882 |  |  | 4m |  | 2 | 4 | NORMAL | CLOSED
2khm9p6 | Custom Fields | 2khm9nr | Onboarding Task | https://app.clickup.com/t/2khm9nr | Suporno Sarkar | 2.6823 |  |  | 6m |  | 2 | 4 | NORMAL | CLOSED
2khm9p7 | Dashboards at a high level to measure your team's progress | 2khm9nr | Onboarding Task | https://app.clickup.com/t/2khm9nr | Suporno Sarkar | 2.2352 |  |  | 5m |  | 2 | 4 | NORMAL | CLOSED
2khm9pa | Managing ClickUp Notifications | 2khm9nr | Onboarding Task | https://app.clickup.com/t/2khm9nr | Suporno Sarkar | 1.7882 |  |  | 4m |  | 2 | 4 | NORMAL | CLOSED
2khm9pb | How to make social media posts | 2khm9nr | Onboarding Task | https://app.clickup.com/t/2khm9nr | Suporno Sarkar | 1.3411 |  |  | 3m |  | 2 | 4 | NORMAL | CLOSED
2khm9pc | How To Reduce Discord Notifications | 2khm9nr | Onboarding Task | https://app.clickup.com/t/2khm9nr | Suporno Sarkar | 1.3411 |  |  | 3m |  | 2 | 4 | NORMAL | CLOSED
2khm9pd | Disable Hot Keys for Better Linking to Documents | 2khm9nr | Onboarding Task | https://app.clickup.com/t/2khm9nr | Suporno Sarkar | 1.3411 |  |  | 3m |  | 2 | 4 | NORMAL | CLOSED
2khm9pe | The ClickUp Chrome Extension | 2khm9nr | Onboarding Task | https://app.clickup.com/t/2khm9nr | Suporno Sarkar | 2.2352 |  |  | 5m |  | 2 | 4 | NORMAL | CLOSED
2khm9ph | Collaborating with tasks | 2khm9nr | Onboarding Task | https://app.clickup.com/t/2khm9nr | Suporno Sarkar | 0.6386 |  |  | 5m |  | 1 | 3 | LOW | CLOSED
2khm9pj | ClickUp Views | 2khm9nr | Onboarding Task | https://app.clickup.com/t/2khm9nr | Suporno Sarkar | 0.5109 |  |  | 4m |  | 1 | 3 | LOW | CLOSED
2khm9pk | Weekly Team Goals | 2khm9nr | Onboarding Task | https://app.clickup.com/t/2khm9nr | Suporno Sarkar | 0.3832 |  |  | 3m |  | 1 | 3 | LOW | CLOSED
2khm9p2 | Communication with your team in ClickUp | 2khm9nr | Onboarding Task | https://app.clickup.com/t/2khm9nr | Suporno Sarkar | 0.1916 |  |  | 3m |  | 1 | 2 | HIGH | CLOSED
2khm9pm | Do this last: How would you improve the onboarding process? | 2khm9nr | Onboarding Task | https://app.clickup.com/t/2khm9nr | Suporno Sarkar | 12.134 |  |  | 10m |  | 4 | 5 | HIGH | CLOSED
Nikhil Yadala |  |  |  |  | Total: | 53.6452
Task ID | Task Name | Parent ID | Parent Name | Parent URL | Assignee | Bounty (formula) | TX URL (url) | Sent Tokens (currency) | Time Estimate | Time Logged | Urgency (1-5) (number) | Importance (1-5) (number) | Priority | Status
25efmje | Add $GCURES to MetaMask |  |  |  | Nikhil Yadala | 13.4113 |  |  | 15m |  | 3 | 5 | HIGH | CLOSED
25efmj1 | Add CureDAO Calendar to Google Calendar |  |  |  | Nikhil Yadala | 2.6823 |  |  | 3m |  | 3 | 5 | HIGH | CLOSED
25efmjk | How To Reduce Discord Notifications |  |  |  | Nikhil Yadala | 2.6823 |  |  | 3m |  | 3 | 5 | HIGH | CLOSED
25efmjm | How to make social media posts |  |  |  | Nikhil Yadala | 1.5327 |  |  | 3m |  | 3 | 3 | NORMAL | CLOSED
25efmjh | How to Use Github |  |  |  | Nikhil Yadala | 2.1075 |  |  | 3m |  | 3 | 4 | NORMAL | CLOSED
25efmhz | Filter and sort your tasks |  |  |  | Nikhil Yadala | 2.1075 |  |  | 3m |  | 3 | 4 | NORMAL | CLOSED
Mike Sinn |  |  |  |  | Total: | 24.5236
Task ID | Task Name | Parent ID | Parent Name | Parent URL | Assignee | Bounty (formula) | TX URL (url) | Sent Tokens (currency) | Time Estimate | Time Logged | Urgency (1-5) (number) | Importance (1-5) (number) | Priority | Status
2gugq8r | Create Curobot Repo |  |  |  | Mike Sinn | 80.4678 |  |  | 3h |  | 2 | 4 | HIGH | CLOSED
2hbp75u | Draft Whitepaper |  |  |  | Mike Sinn | 0 |  |  |  |  | 5 | 5 |  | CLOSED
2j8bf80 | Foresight Institute |  |  |  | Mike Sinn | 145.6084 |  |  | 2h | 2h | 4 | 5 | URGENT | CLOSED [WON]
2hwt88e | determine discover | 2hwt889 | Site terminology | https://app.clickup.com/t/2hwt889 | Mike Sinn | 0 | [7 empty] | CLOSED
2pwz0y0 | Respond to Deiter from Heales |  |  |  | Mike Sinn | 3.5125 |  |  | 5m |  | 3 | 4 | HIGH | CLOSED
2juyga9 | Add to Clickup | 2juyga2 | Shan | https://app.clickup.com/t/2juyga2 | Mike Sinn | 7.6636 |  |  | 5m |  | 5 | 5 |  | CLOSED
2juyga5 | Invite and add to appropriate GitHub teams | 2juyga2 | Shan | https://app.clickup.com/t/2juyga2 | Mike Sinn | 4.5982 |  |  | 3m |  | 5 | 5 |  | CLOSED
2c5wyj0 | Eli onboarding call | 2c5wyhy | Eli | https://app.clickup.com/t/2c5wyhy | Mike Sinn | 72.8042 |  |  | 1h | 1h | 4 | 5 |  | CLOSED
2c5wyj4 | Add Eli to ClickUp | 2c5wyhy | Eli | https://app.clickup.com/t/2c5wyhy | Mike Sinn | 7.2804 |  |  | 6m |  | 4 | 5 |  | CLOSED
2pq8h62 | Create Advisory Board Page Like Attached | 2mrczc9 | Finalize Pitch Deck | https://app.clickup.com/t/2mrczc9 | Mike Sinn | 91.9632 |  |  | 1h | 1h | 5 | 5 | URGENT | CLOSED
2pwz06w | Create Optomitron Project on Website |  |  |  | Mike Sinn | 256.956 |  |  | 4h | 1h | 4 | 5 |  | COMPLETE
2px3j4h | Apply at alliance.xyz and create company FAQ |  |  |  | Mike Sinn | 199.2536 |  |  | 3h 25m | 2h 10m | 5 | 5 | URGENT | SENT
Mark Melnykowycz |  |  |  |  | Total: | 870.1079
Task ID | Task Name | Parent ID | Parent Name | Parent URL | Assignee | Bounty (formula) | TX URL (url) | Sent Tokens (currency) | Time Estimate | Time Logged | Urgency (1-5) (number) | Importance (1-5) (number) | Priority | Status
258zc8m | This is a subtask | 258zc8k | Collaborating with tasks | https://app.clickup.com/t/258zc8k | Mark Melnykowycz | 0 | [7 empty] | CLOSED
Inês Santos Silva |  |  |  |  | Total: | 0
Task ID | Task Name | Parent ID | Parent Name | Parent URL | Assignee | Bounty (formula) | TX URL (url) | Sent Tokens (currency) | Time Estimate | Time Logged | Urgency (1-5) (number) | Importance (1-5) (number) | Priority | Status
2khmtxm | Onboarding Task |  |  |  | Inês Santos Silva | 0 | [6 empty] | HIGH | CLOSED
2khmtxp | Setting due dates to keep your team on track | 2khmtxm | Onboarding Task | https://app.clickup.com/t/2khmtxm | Inês Santos Silva | 4.4704 |  |  | 5m | 4m | 3 | 5 | URGENT | CLOSED
2khmtxq | Home and Prioritizing your team's tasks | 2khmtxm | Onboarding Task | https://app.clickup.com/t/2khmtxm | Inês Santos Silva | 2.6823 |  |  | 3m |  | 3 | 5 | HIGH | CLOSED
2khmtxr | Save your team time with reusable templates! | 2khmtxm | Onboarding Task | https://app.clickup.com/t/2khmtxm | Inês Santos Silva | 2.6823 |  |  | 3m |  | 3 | 5 | HIGH | CLOSED
2khmtxu | Task Statuses and Priorities | 2khmtxm | Onboarding Task | https://app.clickup.com/t/2khmtxm | Inês Santos Silva | 2.6823 |  |  | 3m |  | 3 | 5 | HIGH | CLOSED
2khmtxw | Add $GCURES to MetaMask | 2khmtxm | Onboarding Task | https://app.clickup.com/t/2khmtxm | Inês Santos Silva | 8.9409 |  |  | 10m |  | 3 | 5 | HIGH | CLOSED
2khmtxz | Add CureDAO Calendar to Google Calendar | 2khmtxm | Onboarding Task | https://app.clickup.com/t/2khmtxm | Inês Santos Silva | 0.8941 |  |  | 1m |  | 3 | 5 | HIGH | CLOSED
2khmty1 | Recurring tasks: this task will restart when closed | 2khmtxm | Onboarding Task | https://app.clickup.com/t/2khmtxm | Inês Santos Silva | 1.3411 |  |  | 3m |  | 2 | 4 | NORMAL | CLOSED
2khmty2 | Filter and sort your tasks | 2khmtxm | Onboarding Task | https://app.clickup.com/t/2khmtxm | Inês Santos Silva | 1.3411 |  |  | 3m |  | 2 | 4 | NORMAL | CLOSED
2khmty4 | Organizing with the Hierarchy | 2khmtxm | Onboarding Task | https://app.clickup.com/t/2khmtxm | Inês Santos Silva | 1.7882 |  |  | 4m |  | 2 | 4 | NORMAL | CLOSED
2khmty6 | Custom Fields | 2khmtxm | Onboarding Task | https://app.clickup.com/t/2khmtxm | Inês Santos Silva | 2.6823 |  |  | 6m |  | 2 | 4 | NORMAL | CLOSED
2khmty8 | Dashboards at a high level to measure your team's progress | 2khmtxm | Onboarding Task | https://app.clickup.com/t/2khmtxm | Inês Santos Silva | 2.2352 |  |  | 5m |  | 2 | 4 | NORMAL | CLOSED
2khmty9 | Managing ClickUp Notifications | 2khmtxm | Onboarding Task | https://app.clickup.com/t/2khmtxm | Inês Santos Silva | 1.7882 |  |  | 4m |  | 2 | 4 | NORMAL | CLOSED
2khmtya | How to make social media posts | 2khmtxm | Onboarding Task | https://app.clickup.com/t/2khmtxm | Inês Santos Silva | 1.3411 |  |  | 3m |  | 2 | 4 | NORMAL | CLOSED
2khmtyc | How To Reduce Discord Notifications | 2khmtxm | Onboarding Task | https://app.clickup.com/t/2khmtxm | Inês Santos Silva | 1.3411 |  |  | 3m |  | 2 | 4 | NORMAL | CLOSED
2khmtye | Disable Hot Keys for Better Linking to Documents | 2khmtxm | Onboarding Task | https://app.clickup.com/t/2khmtxm | Inês Santos Silva | 1.3411 |  |  | 3m |  | 2 | 4 | NORMAL | CLOSED
2khmtyf | The ClickUp Chrome Extension | 2khmtxm | Onboarding Task | https://app.clickup.com/t/2khmtxm | Inês Santos Silva | 2.2352 |  |  | 5m |  | 2 | 4 | NORMAL | CLOSED
2khmtyh | Collaborating with tasks | 2khmtxm | Onboarding Task | https://app.clickup.com/t/2khmtxm | Inês Santos Silva | 0.6386 |  |  | 5m |  | 1 | 3 | LOW | CLOSED
2khmtyj | ClickUp Views | 2khmtxm | Onboarding Task | https://app.clickup.com/t/2khmtxm | Inês Santos Silva | 0.5109 |  |  | 4m |  | 1 | 3 | LOW | CLOSED
2khmtyk | Communication with your team in ClickUp | 2khmtxm | Onboarding Task | https://app.clickup.com/t/2khmtxm | Inês Santos Silva | 0.1916 |  |  | 3m |  | 1 | 2 | LOW | CLOSED
2khmtyn | Weekly Team Goals | 2khmtxm | Onboarding Task | https://app.clickup.com/t/2khmtxm | Inês Santos Silva | 0.3832 |  |  | 3m |  | 1 | 3 | LOW | CLOSED
2khmtyp | Do this last: How would you improve the onboarding process? | 2khmtxm | Onboarding Task | https://app.clickup.com/t/2khmtxm | Inês Santos Silva | 12.134 |  |  | 10m |  | 4 | 5 | HIGH | CLOSED
Eli |  |  |  |  | Total: | 53.6452
Task ID | Task Name | Parent ID | Parent Name | Parent URL | Assignee | Bounty (formula) | TX URL (url) | Sent Tokens (currency) | Time Estimate | Time Logged | Urgency (1-5) (number) | Importance (1-5) (number) | Priority | Status
251cvjw | Do this last: How would you improve the onboarding process? | 251cvj3 | Onboarding Task | https://app.clickup.com/t/251cvj3 | Eli | 12.134 |  |  | 10m |  | 4 | 5 | HIGH | COMPLETE
251cvjg | Organizing with the Hierarchy | 251cvj3 | Onboarding Task | https://app.clickup.com/t/251cvj3 | Eli | 1.7882 |  |  | 4m |  | 2 | 4 | NORMAL | COMPLETE
251cvjc | Filter and sort your tasks | 251cvj3 | Onboarding Task | https://app.clickup.com/t/251cvj3 | Eli | 1.3411 |  |  | 3m |  | 2 | 4 | NORMAL | COMPLETE
251cvja | Save your team time with reusable templates! | 251cvj3 | Onboarding Task | https://app.clickup.com/t/251cvj3 | Eli | 2.6823 |  |  | 3m |  | 3 | 5 | HIGH | COMPLETE
251cvj8 | Home and Prioritizing your team's tasks | 251cvj3 | Onboarding Task | https://app.clickup.com/t/251cvj3 | Eli | 2.6823 |  |  | 3m |  | 3 | 5 | HIGH | COMPLETE
251cvjk | Managing ClickUp Notifications | 251cvj3 | Onboarding Task | https://app.clickup.com/t/251cvj3 | Eli | 1.7882 |  |  | 4m |  | 2 | 4 | NORMAL | COMPLETE
251cvjb | Task Statuses and Priorities | 251cvj3 | Onboarding Task | https://app.clickup.com/t/251cvj3 | Eli | 2.6823 |  |  | 3m |  | 3 | 5 | HIGH | COMPLETE
251cvjq | The ClickUp Chrome Extension | 251cvj3 | Onboarding Task | https://app.clickup.com/t/251cvj3 | Eli | 2.2352 |  |  | 5m |  | 2 | 4 | NORMAL | COMPLETE
251cvju | Communication with your team in ClickUp | 251cvj3 | Onboarding Task | https://app.clickup.com/t/251cvj3 | Eli | 0.1916 |  |  | 3m |  | 1 | 2 | LOW | COMPLETE
251cvjv | Weekly Team Goals | 251cvj3 | Onboarding Task | https://app.clickup.com/t/251cvj3 | Eli | 0.3832 |  |  | 3m |  | 1 | 3 | LOW | COMPLETE
251cvjn | How To Reduce Discord Notifications | 251cvj3 | Onboarding Task | https://app.clickup.com/t/251cvj3 | Eli | 1.3411 |  |  | 3m |  | 2 | 4 | NORMAL | COMPLETE
251cvjf | Recurring tasks: this task will restart when closed | 251cvj3 | Onboarding Task | https://app.clickup.com/t/251cvj3 | Eli | 1.3411 |  |  | 3m |  | 2 | 4 | NORMAL | COMPLETE
251cvjm | How to make social media posts | 251cvj3 | Onboarding Task | https://app.clickup.com/t/251cvj3 | Eli | 1.3411 |  |  | 3m |  | 2 | 4 | NORMAL | COMPLETE
251cvjp | Disable Hot Keys for Better Linking to Documents | 251cvj3 | Onboarding Task | https://app.clickup.com/t/251cvj3 | Eli | 1.3411 |  |  | 3m |  | 2 | 4 | NORMAL | COMPLETE
251cvje | Add CureDAO Calendar to Google Calendar | 251cvj3 | Onboarding Task | https://app.clickup.com/t/251cvj3 | Eli | 0.8941 |  |  | 1m |  | 3 | 5 | HIGH | COMPLETE
251cvjd | Add $GCURES to MetaMask | 251cvj3 | Onboarding Task | https://app.clickup.com/t/251cvj3 | Eli | 8.9409 |  |  | 10m |  | 3 | 5 | HIGH | COMPLETE
251cvjr | Collaborating with tasks | 251cvj3 | Onboarding Task | https://app.clickup.com/t/251cvj3 | Eli | 0.6386 |  |  | 5m |  | 1 | 3 | LOW | COMPLETE
251cvjh | Custom Fields | 251cvj3 | Onboarding Task | https://app.clickup.com/t/251cvj3 | Eli | 2.6823 |  |  | 6m |  | 2 | 4 | NORMAL | COMPLETE
251cvjt | ClickUp Views | 251cvj3 | Onboarding Task | https://app.clickup.com/t/251cvj3 | Eli | 0.5109 |  |  | 4m |  | 1 | 3 | LOW | COMPLETE
251cvjj | Dashboards at a high level to measure your team's progress | 251cvj3 | Onboarding Task | https://app.clickup.com/t/251cvj3 | Eli | 2.2352 |  |  | 5m |  | 2 | 4 | NORMAL | COMPLETE
251cvj5 | Setting due dates to keep your team on track | 251cvj3 | Onboarding Task | https://app.clickup.com/t/251cvj3 | Eli | 4.4704 |  |  | 5m |  | 3 | 5 | URGENT | COMPLETE
Brent Nally |  |  |  |  | Total: | 53.6452
Task ID | Task Name | Parent ID | Parent Name | Parent URL | Assignee | Bounty (formula) | TX URL (url) | Sent Tokens (currency) | Time Estimate | Time Logged | Urgency (1-5) (number) | Importance (1-5) (number) | Priority | Status
25m81p4 | ClickUp Views |  |  |  | Brent Nally | 0.3832 |  |  | 3m |  | 1 | 3 | LOW | CLOSED
Andreas Melhede |  |  |  |  | Total: | 0.3832
Task ID | Task Name | Parent ID | Parent Name | Parent URL | Assignee | Bounty (formula) | TX URL (url) | Sent Tokens (currency) | Time Estimate | Time Logged | Urgency (1-5) (number) | Importance (1-5) (number) | Priority | Status
2jdz44j | Determine and include benefits and responsibilities of being a lab coordinator, qualifications, expected time commitments, etc | 2gmvp2u | Create Lab Coordinator Forms | https://app.clickup.com/t/2gmvp2u | Andreas Melhede | 0 | [6 empty] | URGENT | CLOSED
24c5krw | Go through the landing page one more time | 24c5krv | Create another landing page version | https://app.clickup.com/t/24c5krv | Andreas Melhede | 0 | [7 empty] | CLOSED
2juqvrj | Send them 10 $CURE1 Tokens | 2juqvr3 | Blair Z | https://app.clickup.com/t/2juqvr3 | Andreas Melhede | 0 | [7 empty] | CLOSED
2juudkk | Check on deadlines for tasks |  |  |  | Andreas Melhede | 36.4021 |  |  | 30m | 1h 4m | 4 | 5 | URGENT | CLOSED
25zwm68 | Send a Discord message to people including the doc linked above about our intentions | 25zw3yz | Ask people to set due dates for their tasks & add some due dates | https://app.clickup.com/t/25zw3yz | Andreas Melhede | 0 | [7 empty] | CLOSED
265ak7m | Add to Mike's based on the priority of his tasks without asking him. | 25zw3yz | Ask people to set due dates for their tasks & add some due dates | https://app.clickup.com/t/25zw3yz | Andreas Melhede | 0 | [7 empty] | CLOSED
265b1mx | Add people's available hours to: https://app.clickup.com/10641228/v/wl/a4quc-13140 | 265b1mv | Onboard People | https://app.clickup.com/t/265b1mv | Andreas Melhede | 0 | [7 empty] | CLOSED
265b1mz | Send them 10 $GCURES Tokens | 265b1mv | Onboard People | https://app.clickup.com/t/265b1mv | Andreas Melhede | 0 | [7 empty] | CLOSED
265cntz | Send them 10 $CURE1 Tokens | 265cntw | Ashleigh Nicole | https://app.clickup.com/t/265cntw | Andreas Melhede | 0 | [7 empty] | CLOSED
2juyga3 | Send them 10 $CURE1 Tokens | 2juyga2 | Shan | https://app.clickup.com/t/2juyga2 | Andreas Melhede | 0 | [7 empty] | CLOSED
2juyga4 | Schedule an onboarding call | 2juyga2 | Shan | https://app.clickup.com/t/2juyga2 | Andreas Melhede | 0 | [7 empty] | CLOSED
2juyga8 | Add to Discord Labs | 2juyga2 | Shan | https://app.clickup.com/t/2juyga2 | Andreas Melhede | 0 | [7 empty] | CLOSED
265e073 | Add people's available hours to: https://app.clickup.com/10641228/v/wl/a4quc-13140 | 265e072 | Onboard People | https://app.clickup.com/t/265e072 | Andreas Melhede | 0 | [7 empty] | CLOSED
26vyqe7 | Send them 10 $CURE1 Tokens | 26vyqe6 | Keith Comito | https://app.clickup.com/t/26vyqe6 | Andreas Melhede | 0 | [7 empty] | CLOSED
26vyqe9 | Invite and add to appropriate GitHub teams | 26vyqe6 | Keith Comito | https://app.clickup.com/t/26vyqe6 | Andreas Melhede | 0 | [7 empty] | CLOSED
265fnwc | Add to Clickup | 26vyqe6 | Keith Comito | https://app.clickup.com/t/26vyqe6 | Andreas Melhede | 0 | [7 empty] | CLOSED
265fp4v | Onboard People |  |  |  | Andreas Melhede | 430.7582 |  |  | 5h 55m | 5h 55m | 4 | 5 | URGENT | CLOSED
265fp4w | Add people's available hours to: https://app.clickup.com/10641228/v/wl/a4quc-13140 | 265fp4v | Onboard People | https://app.clickup.com/t/265fp4v | Andreas Melhede | 0 | [7 empty] | CLOSED
265fjah | Add the agenda to all the event descriptions | 265fj9v | Restructure the onboarding meeting | https://app.clickup.com/t/265fj9v | Andreas Melhede | 0 | [7 empty] | CLOSED
265gbn2 | Check on deadlines for tasks |  |  |  | Andreas Melhede | 18.2011 |  |  | 15m | 15m | 4 | 5 | URGENT | CLOSED
265j0jk | Check on deadlines for tasks |  |  |  | Andreas Melhede | 18.3926 |  |  | 12m | 12m | 5 | 5 | URGENT | CLOSED
26b4fd8 | Check on deadlines for tasks |  |  |  | Andreas Melhede | 18.3926 |  |  | 12m | 11m | 5 | 5 | URGENT | CLOSED
2bmtuj3 | Send them 10 $CURE1 Tokens | 2bmtuj1 | Anton Pidkuiko | https://app.clickup.com/t/2bmtuj1 | Andreas Melhede | 18.3926 | [7 empty] | CLOSED
26b8j4j | Check on deadlines for tasks |  |  |  | Andreas Melhede | 247.5343 |  |  | 12m | 19m | 5 | 5 | URGENT | CLOSED
26b8jqr | Document Unaccounted Compensation before ClickUp for Andreas Melhede |  |  |  | Andreas Melhede | 52.6032 |  |  | 3h 24m | 3h 23m | 4 | 5 | URGENT | CLOSED
26gt3t1 | Account for the unaccounted compensation after beginning to use ClickUp for Andreas Melhede |  |  |  | Andreas Melhede | 0 |  |  | 45m | 48m | 4 | 5 | HIGH | CLOSED
2buf0e9 | Send them 10 $CURE1 Tokens | 2buf0e7 | Michael | https://app.clickup.com/t/2buf0e7 | Andreas Melhede | 0 | [7 empty] | CLOSED
2buf2bg | Send them 10 $CURE1 Tokens | 2buf2bf | Inês Santos Silva | https://app.clickup.com/t/2buf2bf | Andreas Melhede | 0 | [7 empty] | CLOSED
2buf2bh | Schedule an onboarding call | 2buf2bf | Inês Santos Silva | https://app.clickup.com/t/2buf2bf | Andreas Melhede | 0 | [7 empty] | CLOSED
2buf2bm | Add to Discord Labs | 2buf2bf | Inês Santos Silva | https://app.clickup.com/t/2buf2bf | Andreas Melhede | 0 | [7 empty] | CLOSED
2buf2bp | Add to Clickup | 2buf2bf | Inês Santos Silva | https://app.clickup.com/t/2buf2bf | Andreas Melhede | 0 | [7 empty] | CLOSED
2kc4jdg | Onboarding People & Organizational Work |  |  |  | Andreas Melhede | 539.9645 |  |  | 7h 25m | 7h 51m | 4 | 5 | URGENT | CLOSED
27hyxny | Send them 10 $CURE1 Tokens | 27hyxnx | Suporno Sarkar | https://app.clickup.com/t/27hyxnx | Andreas Melhede | 0 | [7 empty] | CLOSED
27hyxp0 | Schedule an onboarding call | 27hyxnx | Suporno Sarkar | https://app.clickup.com/t/27hyxnx | Andreas Melhede | 0 | [7 empty] | CLOSED
27hyxp1 | Invite and add to appropriate GitHub teams | 27hyxnx | Suporno Sarkar | https://app.clickup.com/t/27hyxnx | Andreas Melhede | 0 | [7 empty] | CLOSED
27hyxp3 | Add "Design Lab" members to the "CureDAO Design Team" in Figma | 27hyxnx | Suporno Sarkar | https://app.clickup.com/t/27hyxnx | Andreas Melhede | 0 | [7 empty] | CLOSED
27hyxp4 | Add to Discord Labs | 27hyxnx | Suporno Sarkar | https://app.clickup.com/t/27hyxnx | Andreas Melhede | 0 | [7 empty] | CLOSED
27hyxp5 | Add to Clickup | 27hyxnx | Suporno Sarkar | https://app.clickup.com/t/27hyxnx | Andreas Melhede | 0 | [7 empty] | CLOSED
2khmew5 | Update Orbit Discord integration |  |  |  | Andreas Melhede | 1.2134 |  |  | 1m | 1m | 4 | 5 | HIGH | CLOSED
2khmhr3 | Compensation for unaccounted work after starting to use ClickUp for Andreas Melhede |  |  |  | Andreas Melhede | 5969.9444 |  |  | 82h | 84h 3m | 4 | 5 | HIGH | CLOSED
24vv0hr | Add availability to Workload | 27hyxnx | Suporno Sarkar | https://app.clickup.com/t/27hyxnx | Andreas Melhede | 0 |  |  | 6m |  |  |  |  | CLOSED
25192tw | Put the Web3 Accelerator Questions and Answers in Q&A List |  |  |  | Andreas Melhede | 29.1217 |  |  | 24m | 24m | 4 | 5 |  | CLOSED
251a10f | Calculate Average Multiplier or Average Rate |  |  |  | Andreas Melhede | 0 | [7 empty] | CLOSED
251a2pd | Add link to payments spreadsheet | 251a2pb | Refund all payments for ClickUp tasks and be good from now on. | https://app.clickup.com/t/251a2pb | Andreas Melhede | 0 | [7 empty] | CLOSED
2khpzve | Onboarding People & Organizational Work |  |  |  | Andreas Melhede | 47.3227 |  |  | 39m | 39m | 4 | 5 | URGENT | CLOSED
251aquc | Send them 10 $CURE1 Tokens | 251aqub | kyle@servingimpact.com | https://app.clickup.com/t/251aqub | Andreas Melhede | 0 | [7 empty] | CLOSED
2kc3wgv | Find an image to use for the "Predictor Search Engine Plugin" and put it into the blog post | 25u3kef | Add Plugin blog posts to the website | https://app.clickup.com/t/25u3kef | Andreas Melhede | 0 | [7 empty] | CLOSED
2khquzq | Check on deadlines for tasks |  |  |  | Andreas Melhede | 21.4581 |  |  | 14m | 14m | 5 | 5 | URGENT | CLOSED
2khqv1p | Update Orbit Discord integration |  |  |  | Andreas Melhede | 1.2134 |  |  | 1m | 1m | 4 | 5 | HIGH | CLOSED
2c5wyhz | Send them 10 $CURE1 Tokens | 2c5wyhy | Eli | https://app.clickup.com/t/2c5wyhy | Andreas Melhede | 0 | [7 empty] | CLOSED
2khtuzz | Onboarding People & Organizational Work |  |  |  | Andreas Melhede | 209.9188 |  |  | 2h 53m | 2h 54m | 4 | 5 | URGENT | CLOSED
2khu5ku | Move the team and advisory board slides from our current design to the Contoso pitch deck slides | 2mrczc9 | Finalize Pitch Deck | https://app.clickup.com/t/2mrczc9 | Andreas Melhede | 91.9632 |  |  | 1h | 60m | 5 | 5 |  | CLOSED
2px3j4h | Apply at alliance.xyz and create company FAQ |  |  |  | Andreas Melhede | 113.4213 |  |  | 3h 25m | 1h 14m | 5 | 5 | URGENT | SENT
2pwz06w | Create Optomitron Project on Website |  |  |  | Andreas Melhede | 34.2608 |  |  | 4h | 8m | 4 | 5 |  | COMPLETE
Akeem Gardner |  |  |  |  | Total: | 7900.479
Task ID | Task Name | Parent ID | Parent Name | Parent URL | Assignee | Bounty (formula) | TX URL (url) | Sent Tokens (currency) | Time Estimate | Time Logged | Urgency (1-5) (number) | Importance (1-5) (number) | Priority | Status
25mc21r | Setting due dates to keep your team on track |  |  |  | Akeem Gardner | 4.4704 |  |  | 5m |  | 3 | 5 | HIGH | CLOSED
Ageless Partners |  |  |  |  | Total: | 4.4704
Task ID | Task Name | Parent ID | Parent Name | Parent URL | Assignee | Bounty (formula) | TX URL (url) | Sent Tokens (currency) | Time Estimate | Time Logged | Urgency (1-5) (number) | Importance (1-5) (number) | Priority | Status
23uzvxh | Improve website grammar and flow |  |  |  | Ageless Partners | 107.2904 |  |  | 2h | 51m | 3 | 5 | NORMAL | CLOSED
258w00n | Setting due dates to keep your team on track |  |  |  | Ageless Partners | 0.9409 |  |  | 10m | 1m | 3 | 5 | HIGH | CLOSED
258w00j | Add CureDAO Calendar to Google Calendar |  |  |  | Ageless Partners | 0.8941 |  |  | 1m | 20m | 3 | 5 | HIGH | CLOSED
258w014 | How To Reduce Discord Notifications |  |  |  | Ageless Partners | 8.9409 |  |  | 10m | 1m | 3 | 5 | HIGH | CLOSED
2n9nju7 | Attach Ageless Partners SVG | 22hb71m | Add partner logos to new website | https://app.clickup.com/t/22hb71m | Ageless Partners | 0 | [7 empty] | CLOSED
2num00d | Upload Ageless Partners Logo SVG (or at least transparent PNG) |  |  |  | Ageless Partners | 8.9409 |  |  | 20m | 1m | 2 | 4 |  | CLOSED
270vp9m | Researched how to add tokens to various blockchains and all the components involved. | 258w00z | Add $GCURES to MetaMask | https://app.clickup.com/t/258w00z | Ageless Partners | 0 | [7 empty] | CLOSED
27cbf8v | On Board Flemming Protocol call |  |  |  | Ageless Partners | 145.6084 |  |  | 2h | 2h | 4 | 5 |  | CLOSED
[5 empty] | Total: | 272.6156
Keith Comito
Task ID | Task Name | Parent ID | Parent Name | Parent URL | Assignee | Bounty (formula) | TX URL (url) | Sent Tokens (currency) | Time Estimate | Time Logged | Urgency (1-5) (number) | Importance (1-5) (number) | Priority | Status
| Do this last: How would you improve the onboarding process? | 2kqcz5q | Onboarding Task | https://app.clickup.com/t/2kqcz5q | Keith Comito | 12.134 |  |  | 10m |  | 4 | 5 | HIGH | COMPLETE
| Organizing with the Hierarchy | 2kqcz5q | Onboarding Task | https://app.clickup.com/t/2kqcz5q | Keith Comito | 1.7882 |  |  | 4m |  | 2 | 4 | NORMAL | COMPLETE
| Filter and sort your tasks | 2kqcz5q | Onboarding Task | https://app.clickup.com/t/2kqcz5q | Keith Comito | 1.3411 |  |  | 3m |  | 2 | 4 | NORMAL | COMPLETE
| Save your team time with reusable templates! | 2kqcz5q | Onboarding Task | https://app.clickup.com/t/2kqcz5q | Keith Comito | 2.6823 |  |  | 3m |  | 3 | 5 | HIGH | COMPLETE
| Home and Prioritizing your team's tasks | 2kqcz5q | Onboarding Task | https://app.clickup.com/t/2kqcz5q | Keith Comito | 2.6823 |  |  | 3m |  | 3 | 5 | HIGH | COMPLETE
| Managing ClickUp Notifications | 2kqcz5q | Onboarding Task | https://app.clickup.com/t/2kqcz5q | Keith Comito | 1.7882 |  |  | 4m |  | 2 | 4 | NORMAL | COMPLETE
| Task Statuses and Priorities | 2kqcz5q | Onboarding Task | https://app.clickup.com/t/2kqcz5q | Keith Comito | 2.6823 |  |  | 3m |  | 3 | 5 | HIGH | COMPLETE
| The ClickUp Chrome Extension | 2kqcz5q | Onboarding Task | https://app.clickup.com/t/2kqcz5q | Keith Comito | 2.2352 |  |  | 5m |  | 2 | 4 | NORMAL | COMPLETE
| Communication with your team in ClickUp | 2kqcz5q | Onboarding Task | https://app.clickup.com/t/2kqcz5q | Keith Comito | 0.1916 |  |  | 3m |  | 1 | 2 | LOW | COMPLETE
| Weekly Team Goals | 2kqcz5q | Onboarding Task | https://app.clickup.com/t/2kqcz5q | Keith Comito | 0.3832 |  |  | 3m |  | 1 | 3 | LOW | COMPLETE
| How To Reduce Discord Notifications | 2kqcz5q | Onboarding Task | https://app.clickup.com/t/2kqcz5q | Keith Comito | 1.3411 |  |  | 3m |  | 2 | 4 | NORMAL | COMPLETE
| Recurring tasks: this task will restart when closed | 2kqcz5q | Onboarding Task | https://app.clickup.com/t/2kqcz5q | Keith Comito | 1.3411 |  |  | 3m |  | 2 | 4 | NORMAL | COMPLETE
| How to make social media posts | 2kqcz5q | Onboarding Task | https://app.clickup.com/t/2kqcz5q | Keith Comito | 1.3411 |  |  | 3m |  | 2 | 4 | NORMAL | COMPLETE
| Disable Hot Keys for Better Linking to Documents | 2kqcz5q | Onboarding Task | https://app.clickup.com/t/2kqcz5q | Keith Comito | 1.3411 |  |  | 3m |  | 2 | 4 | NORMAL | COMPLETE
| Add CureDAO Calendar to Google Calendar | 2kqcz5q | Onboarding Task | https://app.clickup.com/t/2kqcz5q | Keith Comito | 0.8941 |  |  | 1m |  | 3 | 5 | HIGH | COMPLETE
| Add $GCURES to MetaMask | 2kqcz5q | Onboarding Task | https://app.clickup.com/t/2kqcz5q | Keith Comito | 8.9409 |  |  | 10m |  | 3 | 5 | HIGH | COMPLETE
| Collaborating with tasks | 2kqcz5q | Onboarding Task | https://app.clickup.com/t/2kqcz5q | Keith Comito | 0.6386 |  |  | 5m |  | 1 | 3 | LOW | COMPLETE
| Custom Fields | 2kqcz5q | Onboarding Task | https://app.clickup.com/t/2kqcz5q | Keith Comito | 2.6823 |  |  | 6m |  | 2 | 4 | NORMAL | COMPLETE
| ClickUp Views | 2kqcz5q | Onboarding Task | https://app.clickup.com/t/2kqcz5q | Keith Comito | 0.5109 |  |  | 4m |  | 1 | 3 | LOW | COMPLETE
| Dashboards at a high level to measure your team's progress | 2kqcz5q | Onboarding Task | https://app.clickup.com/t/2kqcz5q | Keith Comito | 2.2352 |  |  | 5m |  | 2 | 4 | NORMAL | COMPLETE
| Setting due dates to keep your team on track | 2kqcz5q | Onboarding Task | https://app.clickup.com/t/2kqcz5q | Keith Comito | 4.4704 |  |  | 5m |  | 3 | 5 | URGENT | COMPLETE
[5 empty] | Total: | 53.6452