## Tasks
Richard Sprague
Task ID | Task Name | Parent ID | Parent Name | Parent URL | Assignee | Bounty (formula) | TX URL (url) | Sent Tokens (currency) | Time Estimate | Time Logged | Urgency (1-5) (number) | Importance (1-5) (number) | Priority | Status
2h7xk4n | Discussed Potential Collaboration with MicrobiomePrescription |  |  |  | Richard Sprague | 63.2247 |  |  | 1.5h | 1.5h | 3 | 4 |  | CLOSED
Derek Underwood |  |  |  |  | Total: | 63.2247
Task ID | Task Name | Parent ID | Parent Name | Parent URL | Assignee | Bounty (formula) | TX URL (url) | Sent Tokens (currency) | Time Estimate | Time Logged | Urgency (1-5) (number) | Importance (1-5) (number) | Priority | Status
2dmnh6e | Derek Underwood and CureDAO |  |  |  | Derek Underwood | 72.8042 |  |  | 1h | 1h | 4 | 5 | URGENT | CLOSED
Nonso Michael Ebele-Muolokwu |  |  |  |  | Total: | 72.8042
Task ID | Task Name | Parent ID | Parent Name | Parent URL | Assignee | Bounty (formula) | TX URL (url) | Sent Tokens (currency) | Time Estimate | Time Logged | Urgency (1-5) (number) | Importance (1-5) (number) | Priority | Status
31zvgtv | Organizing with the Hierarchy | 31zvgtr | Onboarding Task | https://app.clickup.com/t/31zvgtr | Nonso Michael Ebele-Muolokwu | 1.3411 |  |  | 3m |  | 2 | 4 | NORMAL | COMPLETE
31zvgtx | Filter and sort your tasks | 31zvgtr | Onboarding Task | https://app.clickup.com/t/31zvgtr | Nonso Michael Ebele-Muolokwu | 1.3411 |  |  | 3m |  | 2 | 4 | NORMAL | COMPLETE
31zvgtz | Task Statuses and Priorities | 31zvgtr | Onboarding Task | https://app.clickup.com/t/31zvgtr | Nonso Michael Ebele-Muolokwu | 2.6823 |  |  | 3m |  | 3 | 5 | HIGH | COMPLETE
31zvgu0 | Setting due dates to keep your team on track | 31zvgtr | Onboarding Task | https://app.clickup.com/t/31zvgtr | Nonso Michael Ebele-Muolokwu | 6.2586 |  |  | 7m |  | 3 | 5 | URGENT | COMPLETE
31zvgu1 | Home and Prioritizing your team's tasks | 31zvgtr | Onboarding Task | https://app.clickup.com/t/31zvgtr | Nonso Michael Ebele-Muolokwu | 4.4704 |  |  | 5m |  | 3 | 5 | HIGH | COMPLETE
Mike Sinn |  |  |  |  | Total: | 16.0935
Task ID | Task Name | Parent ID | Parent Name | Parent URL | Assignee | Bounty (formula) | TX URL (url) | Sent Tokens (currency) | Time Estimate | Time Logged | Urgency (1-5) (number) | Importance (1-5) (number) | Priority | Status
2gugq8p | Create App Builder Repo |  |  |  | Mike Sinn | 103.4386 |  |  | 3h | 8h | 2 | 5 | NORMAL | CLOSED
2gugq88 | Create and Deploy Journal of Citizen Science Repo |  |  |  | Mike Sinn | 218.4126 |  |  | 3h | 5h 51m | 4 | 5 | HIGH | CLOSED
2e0aj45 | Fix Aragon | 2d3p9pp | 🏆 Token Compensation | https://app.clickup.com/t/2d3p9pp | Mike Sinn | 61.3088 |  |  | 2h | 2h | 3 | 3 | LOW | CLOSED
2mcz447 | Document Projected Expenses | 2hbp762 | Edit Business Plan | https://app.clickup.com/t/2hbp762 | Mike Sinn | 367.8528 |  |  | 4h | 4h | 5 | 5 | URGENT | CLOSED
251cwe3 | Fix OAuth Login |  |  |  | Mike Sinn | 291.2168 |  |  | 4h | 3h 59m | 4 | 5 |  | CLOSED
282j5em | Daily Scrum Meeting (Mike) |  |  |  | Mike Sinn | 66.7372 |  |  | 55m | 15m | 4 | 5 |  | CLOSED
2a7g3we | Forever.Today Integration |  |  |  | Mike Sinn | 2042.1578 |  |  | 28h 3m | 28h 3m | 5 | 4 | URGENT | CLOSED
2rhw4kx | Weekly Planning Meeting (Mike) |  |  |  | Mike Sinn | 183.9264 |  |  | 2h |  | 5 | 5 |  | CLOSED
2t3997b | Who's the best entrepreneur you know (besides you) who will start a business in the next year? Share their email if you'd like to introduce them to us |  |  |  | Mike Sinn | 15.3272 |  |  | 10m |  | 5 | 5 | HIGH | CLOSED
2dmhcry | Ekene Umeh and CureDAO |  |  |  | Mike Sinn | 72.8042 |  |  | 1h | 1h | 4 | 5 | URGENT | CLOSED
2rhwn8a | Apply at DeathlessDAO |  |  |  | Mike Sinn | 45.9816 |  |  | 30m | 30m | 5 | 5 | HIGH | CLOSED [WON]
2e5u97q | Tovah and CureDAO |  |  |  | Mike Sinn | 54.6032 |  |  | 45m |  | 5 | 4 | URGENT | CLOSED
2chm50z | What makes this approach more interesting than other similar approaches? |  |  |  | Mike Sinn | 45.9816 |  |  | 30m |  | 5 | 5 |  | CLOSED
2chmh9d | If you had to say what the key innovation your company brings to the table in 1 sentence, what is it? Be specific. |  |  |  | Mike Sinn | 30.6544 |  |  | 20m |  | 5 | 5 |  | CLOSED
2chmkhx | What has been the single biggest achievement for the company thus far? |  |  |  | Mike Sinn | 30.6544 |  |  | 20m |  | 5 | 5 |  | CLOSED
2chmq16 | What is the biggest scientific/technology risk the company still faces? |  |  |  | Mike Sinn | 30.6544 |  |  | 20m |  | 5 | 5 |  | CLOSED
2chmt8e | What is the biggest business risk that the team still faces? |  |  |  | Mike Sinn | 45.9816 |  |  | 30m |  | 5 | 5 |  | CLOSED
2chn3f5 | What do you aim to achieve in the next 1 year? |  |  |  | Mike Sinn | 22.9908 |  |  | 15m |  | 5 | 5 |  | CLOSED
2ebj3gn | Darren Nesbeth and CureDAO |  |  |  | Mike Sinn | 54.6032 |  |  | 45m | 1h | 5 | 4 | URGENT | CLOSED
25cuz3j | Create Predictor Search Engine |  |  |  | Mike Sinn | 728.042 |  |  | 10h | 1h 4m | 4 | 5 | URGENT | CLOSED
2d3076p | Daily Scrum Meeting (Mike) |  |  |  | Mike Sinn | 66.7372 |  |  | 55m | 1h | 4 | 5 |  | CLOSED
2epyzg4 | Triyaksh Mathur and CureDAO |  |  |  | Mike Sinn | 54.6032 |  |  | 45m |  | 4 | 5 | URGENT | CLOSED
2dm12a5 | Daily Scrum Meeting (Mike) |  |  |  | Mike Sinn | 66.7372 |  |  | 55m | 1h | 4 | 5 |  | CLOSED
2ewmv9u | Nonso Michael Ebele-Muolokwu and CureDAO |  |  |  | Mike Sinn | 91.9632 |  |  | 1h | 1h | 5 | 5 | URGENT | CLOSED
2ewrxvc | Jiré Saffron and CureDAO |  |  |  | Mike Sinn | 109.2063 |  |  | 1h 30m | 1h 30m | 4 | 5 | URGENT | CLOSED
3ctvjqq | Daily Scrum Meeting (Mike) |  |  |  | Mike Sinn | 66.7372 |  |  | 55m | 1h | 4 | 5 |  | CLOSED
2f88ke7 | Alex |  |  |  | Mike Sinn | 36.4021 |  |  | 30m |  | 4 | 5 | URGENT | CLOSED
3dw0duw | Daily Scrum Meeting (Mike) |  |  |  | Mike Sinn | 66.7372 |  |  | 55m | 2h | 4 | 5 |  | CLOSED
2f1zx94 | Weekly Planning Meeting (Mike) |  |  |  | Mike Sinn | 114.954 |  |  | 2h | 2h | 4 | 4 |  | CLOSED
2f200a3 | Daily Scrum Meeting (Mike) |  |  |  | Mike Sinn | 66.7372 |  |  | 55m | 1h | 4 | 5 |  | CLOSED
2f200jk | Daily Scrum Meeting (Mike) |  |  |  | Mike Sinn | 52.6873 |  |  | 55m | 1h | 4 | 4 |  | CLOSED
2f81c6d | Jiré and CureDAO |  |  |  | Mike Sinn | 72.8042 |  |  | 1h | 1h | 4 | 5 | URGENT | CLOSED
2889r9x | Make Funding Options Comparison |  |  |  | Mike Sinn | 459.816 |  |  | 5h | 5h | 5 | 5 |  | CLOSED
2fkpm33 | Andre Chagwedera and CureDAO |  |  |  | Mike Sinn | 57.477 |  |  | 1h | 1h | 4 | 4 | URGENT | CLOSED
2yymrae | Add to Discord Labs | 2yymra7 | Ahire Tersoo David | https://app.clickup.com/t/2yymra7 | Mike Sinn | 6.1309 |  |  | 4m |  | 5 | 5 |  | CLOSED
2yymrab | Invite and add to appropriate GitHub teams | 2yymra7 | Ahire Tersoo David | https://app.clickup.com/t/2yymra7 | Mike Sinn | 6.1309 |  |  | 4m |  | 5 | 5 |  | CLOSED
2hkb02r | Add to Clickup, make them guests, create onboarding tasks for them, and grant them access to their onboarding tasks | 2hkb02h | Lucas Jones | https://app.clickup.com/t/2hkb02h | Mike Sinn | 7.6636 |  |  | 5m |  | 5 | 5 |  | CLOSED
2h7xk4n | Discussed Potential Collaboration with MicrobiomePrescription |  |  |  | Mike Sinn | 63.2247 |  |  | 1.5h | 1.5h | 3 | 4 |  | CLOSED
2fz1qf0 | Lucas E Jones and CureDAO |  |  |  | Mike Sinn | 72.8042 |  |  | 1h | 1h | 4 | 5 | URGENT | CLOSED
2dmnh6e | Derek Underwood and CureDAO |  |  |  | Mike Sinn | 72.8042 |  |  | 1h | 1h | 4 | 5 | URGENT | CLOSED
31u5pek | ODLB Web3 x Bio Panel + Networking event |  |  |  | Mike Sinn | 183.9264 |  |  | 2h 37m | 2h 38m | 5 | 5 | URGENT | CLOSED
Martijn van den Broek |  |  |  |  | Total: | 6309.6138
Task ID | Task Name | Parent ID | Parent Name | Parent URL | Assignee | Bounty (formula) | TX URL (url) | Sent Tokens (currency) | Time Estimate | Time Logged | Urgency (1-5) (number) | Importance (1-5) (number) | Priority | Status
2dm1et6 | Import all GCures transactions for accounting to Postgres or Airtable with Covalent API https://www.covalenthq.com/platform/#/ |  |  |  | Martijn van den Broek | 574.77 |  |  | 10h | 10h | 4 | 4 | NORMAL | CLOSED
Lukas Vogel |  |  |  |  | Total: | 574.77
Task ID | Task Name | Parent ID | Parent Name | Parent URL | Assignee | Bounty (formula) | TX URL (url) | Sent Tokens (currency) | Time Estimate | Time Logged | Urgency (1-5) (number) | Importance (1-5) (number) | Priority | Status
2m7jfkq | 2nd (and third+) opinion on current legal structures | 2nn07qm | Establish a legal entity | https://app.clickup.com/t/2nn07qm | Lukas Vogel | 689.724 |  |  |  | 7h 30m | 5 | 5 | HIGH | COMPLETE
31mag8a | Onboarding People & Organizational Work |  |  |  | Lukas Vogel | 331.3499 |  |  | 47h 58m | 47h 58m | 4 | 5 | URGENT | CLOSED
Lucas Jones |  |  |  |  | Total: | 1021.0739
Task ID | Task Name | Parent ID | Parent Name | Parent URL | Assignee | Bounty (formula) | TX URL (url) | Sent Tokens (currency) | Time Estimate | Time Logged | Urgency (1-5) (number) | Importance (1-5) (number) | Priority | Status
2hrz9te | Onboarding Task |  |  |  | Lucas Jones | 0 |  |  |  | 1h 17m |  |  | HIGH | COMPLETE
2hrz9tg | Organizing with the Hierarchy | 2hrz9te | Onboarding Task | https://app.clickup.com/t/2hrz9te | Lucas Jones | 1.3411 |  |  | 3m |  | 2 | 4 | NORMAL | COMPLETE
2hrz9tj | Filter and sort your tasks | 2hrz9te | Onboarding Task | https://app.clickup.com/t/2hrz9te | Lucas Jones | 1.3411 |  |  | 3m |  | 2 | 4 | NORMAL | COMPLETE
2hrz9tk | Task Statuses and Priorities | 2hrz9te | Onboarding Task | https://app.clickup.com/t/2hrz9te | Lucas Jones | 2.6823 |  |  | 3m | 2m | 3 | 5 | HIGH | COMPLETE
2hrz9tn | Setting due dates to keep your team on track | 2hrz9te | Onboarding Task | https://app.clickup.com/t/2hrz9te | Lucas Jones | 6.2586 |  |  | 7m |  | 3 | 5 | URGENT | COMPLETE
2hrz9tq | Home and Prioritizing your team's tasks | 2hrz9te | Onboarding Task | https://app.clickup.com/t/2hrz9te | Lucas Jones | 4.4704 |  |  | 5m |  | 3 | 5 | HIGH | COMPLETE
2hrz9tu | Collaborating with tasks | 2hrz9te | Onboarding Task | https://app.clickup.com/t/2hrz9te | Lucas Jones | 0.6386 |  |  | 5m |  | 1 | 3 | LOW | COMPLETE
2hrz9tw | Recurring tasks: this task will restart when closed | 2hrz9te | Onboarding Task | https://app.clickup.com/t/2hrz9te | Lucas Jones | 0.8941 |  |  | 2m |  | 2 | 4 | NORMAL | COMPLETE
2hrz9tx | Managing ClickUp Notifications | 2hrz9te | Onboarding Task | https://app.clickup.com/t/2hrz9te | Lucas Jones | 1.3411 |  |  | 3m |  | 2 | 4 | HIGH | COMPLETE
2hrz9ty | Communication with your team in ClickUp | 2hrz9te | Onboarding Task | https://app.clickup.com/t/2hrz9te | Lucas Jones | 2.2352 |  |  | 5m |  | 2 | 4 | LOW | COMPLETE
2hrz9tz | Weekly Team Goals | 2hrz9te | Onboarding Task | https://app.clickup.com/t/2hrz9te | Lucas Jones | 0.3832 |  |  | 3m |  | 1 | 3 | LOW | COMPLETE
2hrz9u3 | Save your team time with reusable templates! | 2hrz9te | Onboarding Task | https://app.clickup.com/t/2hrz9te | Lucas Jones | 2.6823 |  |  | 3m |  | 3 | 5 | HIGH | COMPLETE
2hrz9u5 | Custom Fields | 2hrz9te | Onboarding Task | https://app.clickup.com/t/2hrz9te | Lucas Jones | 3.1293 |  |  | 7m |  | 2 | 4 | NORMAL | COMPLETE
2hrz9u6 | Dashboards at a high level to measure your team's progress | 2hrz9te | Onboarding Task | https://app.clickup.com/t/2hrz9te | Lucas Jones | 3.1293 |  |  | 7m |  | 2 | 4 | NORMAL | COMPLETE
2hrz9u7 | Disable Hot Keys for Better Linking to Documents | 2hrz9te | Onboarding Task | https://app.clickup.com/t/2hrz9te | Lucas Jones | 1.3411 |  |  | 3m |  | 2 | 4 | NORMAL | COMPLETE
2hrz9u8 | ClickUp Views | 2hrz9te | Onboarding Task | https://app.clickup.com/t/2hrz9te | Lucas Jones | 0.6386 |  |  | 5m |  | 1 | 3 | LOW | COMPLETE
2hrz9ua | The ClickUp Chrome Extension | 2hrz9te | Onboarding Task | https://app.clickup.com/t/2hrz9te | Lucas Jones | 2.2352 |  |  | 5m |  | 2 | 4 | NORMAL | COMPLETE
2hrz9uc | How to make social media posts for CureDAO | 2hrz9te | Onboarding Task | https://app.clickup.com/t/2hrz9te | Lucas Jones | 1.3411 |  |  | 3m |  | 2 | 4 | NORMAL | COMPLETE
2hrz9ud | How To Reduce Discord Notifications | 2hrz9te | Onboarding Task | https://app.clickup.com/t/2hrz9te | Lucas Jones | 1.3411 |  |  | 3m |  | 2 | 4 | NORMAL | COMPLETE
2hrz9ue | Add CureDAO's Calendar to Google Calendar | 2hrz9te | Onboarding Task | https://app.clickup.com/t/2hrz9te | Lucas Jones | 0.8941 |  |  | 1m |  | 3 | 5 | HIGH | COMPLETE
2hrz9uf | Add $GCURES to MetaMask | 2hrz9te | Onboarding Task | https://app.clickup.com/t/2hrz9te | Lucas Jones | 8.9409 |  |  | 10m |  | 3 | 5 | HIGH | COMPLETE
2hrz9ug | Schedule a call to find your first quest and get started! | 2hrz9te | Onboarding Task | https://app.clickup.com/t/2hrz9te | Lucas Jones | 3.6402 |  |  | 3m |  | 4 | 5 | URGENT | COMPLETE
2hrz9uh | Do this last: How would you improve the onboarding process? | 2hrz9te | Onboarding Task | https://app.clickup.com/t/2hrz9te | Lucas Jones | 10.9206 |  |  | 9m |  | 4 | 5 | HIGH | COMPLETE
2fz1qf0 | Lucas E Jones and CureDAO |  |  |  | Lucas Jones | 72.8042 |  |  | 1h | 1h | 4 | 5 | URGENT | CLOSED
Keith Comito |  |  |  |  | Total: | 134.6237
Task ID | Task Name | Parent ID | Parent Name | Parent URL | Assignee | Bounty (formula) | TX URL (url) | Sent Tokens (currency) | Time Estimate | Time Logged | Urgency (1-5) (number) | Importance (1-5) (number) | Priority | Status
2h264yv | Speaking with Petr and Jyothi from LongevityTech.Fund about CureDAO, and connecting with Mike S. for follow up. |  |  |  | Keith Comito | 145.6084 |  |  | 2h | 2h | 4 | 5 |  | CLOSED [WON]
2hdnvv9 | Discussing with Patrick Joyce of ResearchHub details of potential interoperation points, and connecting with Mike S. |  |  |  | Keith Comito | 72.8042 |  |  | 1h | 1h | 4 | 5 |  | CLOSED [WON]
2hdnvzw | Discussion with CTO of Enjin on potentials to integrate Efinity and CureDAO, connecting with Mike S. |  |  |  | Keith Comito | 114.954 |  |  | 2h | 2h | 4 | 4 |  | CLOSED [WON]
Jefferson Usianene |  |  |  |  | Total: | 333.3666
Task ID | Task Name | Parent ID | Parent Name | Parent URL | Assignee | Bounty (formula) | TX URL (url) | Sent Tokens (currency) | Time Estimate | Time Logged | Urgency (1-5) (number) | Importance (1-5) (number) | Priority | Status
31enxf8 | Filter and sort your tasks | 31enxf4 | Onboarding Task | https://app.clickup.com/t/31enxf4 | Jefferson Usianene | 1.3411 |  |  | 3m |  | 2 | 4 | NORMAL | COMPLETE
31enxf9 | Task Statuses and Priorities | 31enxf4 | Onboarding Task | https://app.clickup.com/t/31enxf4 | Jefferson Usianene | 2.6823 |  |  | 3m |  | 3 | 5 | HIGH | COMPLETE
31enxfa | Setting due dates to keep your team on track | 31enxf4 | Onboarding Task | https://app.clickup.com/t/31enxf4 | Jefferson Usianene | 6.2586 |  |  | 7m |  | 3 | 5 | URGENT | COMPLETE
31enxf6 | Organizing with the Hierarchy | 31enxf4 | Onboarding Task | https://app.clickup.com/t/31enxf4 | Jefferson Usianene | 1.3411 |  |  | 3m | 1m | 2 | 4 | NORMAL | COMPLETE
Andreas Melhede |  |  |  |  | Total: | 11.6231
Task ID | Task Name | Parent ID | Parent Name | Parent URL | Assignee | Bounty (formula) | TX URL (url) | Sent Tokens (currency) | Time Estimate | Time Logged | Urgency (1-5) (number) | Importance (1-5) (number) | Priority | Status
2vk948k | Develop Plan for getting on Binance Launchpad |  |  |  | Andreas Melhede | 421.498 |  |  | 4h 35m | 4h 35m | 5 | 5 | URGENT | CLOSED
30j2k5w | Send 10 $CURE1 Tokens & let them know | 30j2k5u | Lanre Daniels | https://app.clickup.com/t/30j2k5u | Andreas Melhede | 0 | [7 empty] | CLOSED
30j2k64 | Add to Clickup, make them guests, create onboarding tasks for them, and grant them access to their onboarding tasks | 30j2k5u | Lanre Daniels | https://app.clickup.com/t/30j2k5u | Andreas Melhede | 0 | [7 empty] | CLOSED
30xcchm | Add to Clickup, make them guests, create onboarding tasks for them, and grant them access to their onboarding tasks | 30xccha | Nonso Michael Ebele-Muolokwu | https://app.clickup.com/t/30xccha | Andreas Melhede | 0 | [7 empty] | CLOSED
31392ww | Compensate people with tokens |  |  |  | Andreas Melhede | 125.683 |  |  | 1h 22m | 1h 22m | 5 | 5 | URGENT | CLOSED
31me4q9 | Update Orbit Discord integration |  |  |  | Andreas Melhede | 0 |  |  | 1m |  | 4 | 4 | HIGH | CLOSED
31me86y | Check on deadlines for tasks |  |  |  | Andreas Melhede | 3.0654 |  |  | 2m | 2m | 5 | 5 | URGENT | CLOSED
31u3a6t | Update Orbit Discord integration |  |  |  | Andreas Melhede | 0 |  |  | 1m |  | 4 | 4 | HIGH | CLOSED
31u3w81 | Check on deadlines for tasks |  |  |  | Andreas Melhede | 9.1963 |  |  | 6m | 7m | 5 | 5 | URGENT | CLOSED
31ztdgu | Update Orbit Discord integration |  |  |  | Andreas Melhede | 0 |  |  | 1m |  | 4 | 4 | HIGH | CLOSED
31ztp26 | Check on deadlines for tasks |  |  |  | Andreas Melhede | 3.0654 |  |  | 2m | 3m | 5 | 5 | URGENT | CLOSED
2rx9840 | Free Accelerator & Capital - Lightship Capital |  |  |  | Andreas Melhede | 18.3926 |  |  | 12m | 13m | 5 | 5 | HIGH | CLOSED [WON]
325cxcn | Update Orbit Discord integration |  |  |  | Andreas Melhede | 0 |  |  | 1m |  | 4 | 4 | HIGH | CLOSED
325d1pu | Check on deadlines for tasks |  |  |  | Andreas Melhede | 10.729 |  |  | 7m | 7m | 5 | 5 | URGENT | CLOSED
2rx9uya | Founders Space |  |  |  | Andreas Melhede | 18.3926 |  |  | 12m | 13m | 5 | 5 | NORMAL | CLOSED [WON]
2nf6x8r | WEBIT FOUNDERS GAMES 2022 |  |  |  | Andreas Melhede | 137.9448 |  |  | 1h 30m | 1h 30m | 5 | 5 |  | CLOSED [WON]
2weet3t | https://www.antler.co/web3 |  |  |  | Andreas Melhede | 70.5051 |  |  | 46m | 46m | 5 | 5 |  | CLOSED [WON]
2hkb02j | Send 10 $CURE1 Tokens & let them know | 2hkb02h | Lucas Jones | https://app.clickup.com/t/2hkb02h | Andreas Melhede | 0 | [7 empty] | CLOSED
2yymraa | Schedule an onboarding call | 2yymra7 | Ahire Tersoo David | https://app.clickup.com/t/2yymra7 | Andreas Melhede | 0 | [7 empty] | CLOSED
325ma3x | Update Orbit Discord integration |  |  |  | Andreas Melhede | 0 |  |  | 1m |  | 4 | 4 | HIGH | CLOSED
325mcmp | Check on deadlines for tasks |  |  |  | Andreas Melhede | 12.2618 |  |  | 8m | 8m | 5 | 5 | URGENT | CLOSED
2acyb4p | BioDAO The global biotech economy enabled by Web3 |  |  |  | Andreas Melhede | 44.4489 |  |  | 29m | 29m | 5 | 5 |  | CLOSED [WON]
2h7uzb3 | Clearer Thinking Regrants ¦ GuidedTrack ¦ https://www.guidedtrack.com/programs/ftxtl1j/run |  |  |  | Andreas Melhede | 87.365 |  |  | 57m | 57m | 5 | 5 |  | CLOSED [WON]
2rvz52n | Plug and Play Tech Center |  |  |  | Andreas Melhede | 4.5982 |  |  | 3m | 4m | 5 | 5 |  | CLOSED [WON]
2dzc9ma | https://newscience.org/one-year-fellowship/ |  |  |  | Andreas Melhede | 18.3926 |  |  | 12m | 12m | 5 | 5 |  | CLOSED [WON]
2ej2m6t | Altair’s Startup Program |  |  |  | Andreas Melhede | 9.1963 |  |  | 6m | 6m | 5 | 5 |  | CLOSED [WON]
2yrwzjv | Deepfunding ¦ https://deepfunding.ai/ |  |  |  | Andreas Melhede | 113.4213 |  |  | 1h 14m | 1h 15m | 5 | 5 |  | CLOSED [WON]
2yrvrm8 | SeedClub SC05 Interest Form ¦ https://airtable.com/shr35dCkkt6Dxy7OY?utm_source=substack&utm_medium=email |  |  |  | Andreas Melhede | 9.1963 |  |  | 6m | 7m | 5 | 5 |  | CLOSED [WON]
32b6ry9 | Update Orbit Discord integration |  |  |  | Andreas Melhede | 0 |  |  | 1m |  | 4 | 4 | HIGH | CLOSED
32b6vcd | Check on deadlines for tasks |  |  |  | Andreas Melhede | 12.2618 |  |  | 8m | 8m | 5 | 5 | URGENT | CLOSED
31zvz14 | How would you spend an initial seed investment of $250,000 and over what time frame? |  |  |  | Andreas Melhede | 22.9908 |  |  | 15m | 16m | 5 | 5 | URGENT | CLOSED
31zvz2w | To what stage would the $250,000 take you to and what would next steps look like? |  |  |  | Andreas Melhede | 19.9254 |  |  | 13m | 13m | 5 | 5 | URGENT | CLOSED
31u5pek | ODLB Web3 x Bio Panel + Networking event |  |  |  | Andreas Melhede | 56.7106 |  |  | 2h 37m | 2h 38m | 5 | 5 | URGENT | CLOSED
31mag8a | Onboarding People & Organizational Work |  |  |  | Andreas Melhede | 3160.8249 |  |  | 47h 58m | 47h 58m | 4 | 5 | URGENT | CLOSED
[5 empty] | Total: | 4390.0661