## Tasks
Sandra Ashipala
Task ID | Task Name | Parent ID | Parent Name | Parent URL | Assignee | Bounty (formula) | TX URL (url) | Sent Tokens (currency) | Time Estimate | Time Logged | Urgency (1-5) (number) | Importance (1-5) (number) | Priority | Status
24pkudj | Fix Curbot Bugs |  |  |  | Sandra Ashipala | 97.0723 |  |  | 1h 5m | 10h 21m | 4 | 5 | HIGH | CLOSED
Tovah Wolf |  |  |  |  | Total: | 97.0723
Task ID | Task Name | Parent ID | Parent Name | Parent URL | Assignee | Bounty (formula) | TX URL (url) | Sent Tokens (currency) | Time Estimate | Time Logged | Urgency (1-5) (number) | Importance (1-5) (number) | Priority | Status
2vk41th | Do this last: How would you improve the onboarding process? | 2vk41rr | Onboarding Task | https://app.clickup.com/t/2vk41rr | Tovah Wolf | 10.9206 |  |  | 9m |  | 4 | 5 | HIGH | COMPLETE
2vk41rr | Onboarding Task |  |  |  | Tovah Wolf | 0 | [6 empty] | HIGH | COMPLETE
Nonso Michael Ebele-Muolokwu |  |  |  |  | Total: | 10.9206
Task ID | Task Name | Parent ID | Parent Name | Parent URL | Assignee | Bounty (formula) | TX URL (url) | Sent Tokens (currency) | Time Estimate | Time Logged | Urgency (1-5) (number) | Importance (1-5) (number) | Priority | Status
31zvgu8 | Collaborating with tasks | 31zvgtr | Onboarding Task | https://app.clickup.com/t/31zvgtr | Nonso Michael Ebele-Muolokwu | 0.6386 |  |  | 5m |  | 1 | 3 | LOW | COMPLETE
31zvgub | Recurring tasks: this task will restart when closed | 31zvgtr | Onboarding Task | https://app.clickup.com/t/31zvgtr | Nonso Michael Ebele-Muolokwu | 0.8941 |  |  | 2m |  | 2 | 4 | NORMAL | COMPLETE
31zvguc | Managing ClickUp Notifications | 31zvgtr | Onboarding Task | https://app.clickup.com/t/31zvgtr | Nonso Michael Ebele-Muolokwu | 1.3411 |  |  | 3m |  | 2 | 4 | HIGH | COMPLETE
31zvgud | Communication with your team in ClickUp | 31zvgtr | Onboarding Task | https://app.clickup.com/t/31zvgtr | Nonso Michael Ebele-Muolokwu | 2.2352 |  |  | 5m |  | 2 | 4 | LOW | COMPLETE
31zvguf | Weekly Team Goals | 31zvgtr | Onboarding Task | https://app.clickup.com/t/31zvgtr | Nonso Michael Ebele-Muolokwu | 0.3832 |  |  | 3m |  | 1 | 3 | LOW | COMPLETE
31zvguh | Save your team time with reusable templates! | 31zvgtr | Onboarding Task | https://app.clickup.com/t/31zvgtr | Nonso Michael Ebele-Muolokwu | 2.6823 |  |  | 3m |  | 3 | 5 | HIGH | COMPLETE
31zvguj | Custom Fields | 31zvgtr | Onboarding Task | https://app.clickup.com/t/31zvgtr | Nonso Michael Ebele-Muolokwu | 3.1293 |  |  | 7m |  | 2 | 4 | NORMAL | COMPLETE
31zvgun | Dashboards at a high level to measure your team's progress | 31zvgtr | Onboarding Task | https://app.clickup.com/t/31zvgtr | Nonso Michael Ebele-Muolokwu | 3.1293 |  |  | 7m |  | 2 | 4 | NORMAL | COMPLETE
31zvguq | Disable Hot Keys for Better Linking to Documents | 31zvgtr | Onboarding Task | https://app.clickup.com/t/31zvgtr | Nonso Michael Ebele-Muolokwu | 1.3411 |  |  | 3m |  | 2 | 4 | NORMAL | COMPLETE
31zvguu | ClickUp Views | 31zvgtr | Onboarding Task | https://app.clickup.com/t/31zvgtr | Nonso Michael Ebele-Muolokwu | 0.6386 |  |  | 5m |  | 1 | 3 | LOW | COMPLETE
31zvgux | The ClickUp Chrome Extension | 31zvgtr | Onboarding Task | https://app.clickup.com/t/31zvgtr | Nonso Michael Ebele-Muolokwu | 2.2352 |  |  | 5m |  | 2 | 4 | NORMAL | COMPLETE
31zvguy | How to make social media posts for CureDAO | 31zvgtr | Onboarding Task | https://app.clickup.com/t/31zvgtr | Nonso Michael Ebele-Muolokwu | 1.3411 |  |  | 3m |  | 2 | 4 | NORMAL | COMPLETE
31zvguz | How To Reduce Discord Notifications | 31zvgtr | Onboarding Task | https://app.clickup.com/t/31zvgtr | Nonso Michael Ebele-Muolokwu | 1.3411 |  |  | 3m |  | 2 | 4 | NORMAL | COMPLETE
31zvgv1 | Add CureDAO's Calendar to Google Calendar | 31zvgtr | Onboarding Task | https://app.clickup.com/t/31zvgtr | Nonso Michael Ebele-Muolokwu | 0.8941 |  |  | 1m |  | 3 | 5 | HIGH | COMPLETE
31zvgv3 | Add $GCURES to MetaMask | 31zvgtr | Onboarding Task | https://app.clickup.com/t/31zvgtr | Nonso Michael Ebele-Muolokwu | 8.9409 |  |  | 10m |  | 3 | 5 | HIGH | COMPLETE
Mike Sinn |  |  |  |  | Total: | 31.1652
Task ID | Task Name | Parent ID | Parent Name | Parent URL | Assignee | Bounty (formula) | TX URL (url) | Sent Tokens (currency) | Time Estimate | Time Logged | Urgency (1-5) (number) | Importance (1-5) (number) | Priority | Status
2epwzvq | Mark Melnykowycz and CureDAO |  |  |  | Mike Sinn | 36.4021 |  |  | 30m | 30m | 4 | 5 | URGENT | CLOSED
2epxrkk | Ekene Umeh and CureDAO |  |  |  | Mike Sinn | 36.4021 |  |  | 30m | 30m | 4 | 5 | URGENT | CLOSED
3c8mfz0 | Daily Scrum Meeting (Mike) |  |  |  | Mike Sinn | 66.7372 |  |  | 55m | 3h | 4 | 5 |  | CLOSED
2ftabjm | Tovah and CureDAO |  |  |  | Mike Sinn | 36.4021 |  |  | 30m |  | 4 | 5 | URGENT | CLOSED
2hyu5u1 | Anima - Export to HTML, React & Vue Code |  |  |  | Mike Sinn | 7.6636 |  |  | 15m | 15m | 3 | 3 |  | DONE
3f47hf3 | Daily Scrum Meeting (Mike) |  |  |  | Mike Sinn | 52.6873 |  |  | 55m | 1h | 4 | 4 |  | CLOSED
2hdv5c8 | Schedule an onboarding call | 2hdv5bj | Evan Basson AKA MotionFactory | https://app.clickup.com/t/2hdv5bj | Mike Sinn | 6.067 |  |  | 5m |  | 4 | 5 |  | CLOSED
2d2ru28 | Supernova : Internet Computer Web3 Hackathon - Devpost ¦ https://supernova.devpost.com/ |  |  |  | Mike Sinn | 91.9632 |  |  | 1h | 1h | 5 | 5 |  | CLOSED
2hkb02n | Add "Design Lab" members to the "CureDAO Design Team" in Figma | 2hkb02h | Lucas Jones | https://app.clickup.com/t/2hkb02h | Mike Sinn | 9.1963 |  |  | 6m |  | 5 | 5 |  | CLOSED
2yymrah | Add their weekly available hours here: https://app.clickup.com/10641228/v/wl/a4quc-13140 | 2yymra7 | Ahire Tersoo David | https://app.clickup.com/t/2yymra7 | Mike Sinn | 7.2804 |  |  | 6m |  | 4 | 5 |  | CLOSED
3fnbv7u | Daily Scrum Meeting (Mike) |  |  |  | Mike Sinn | 52.6873 |  |  | 55m | 30m | 4 | 4 |  | CLOSED
2hdv5d4 | Add to Clickup, make them guests, create onboarding tasks for them, and grant them access to their onboarding tasks | 2hdv5bj | Evan Basson AKA MotionFactory | https://app.clickup.com/t/2hdv5bj | Mike Sinn | 6.067 |  |  | 5m |  | 4 | 5 |  | CLOSED
24pkudj | Fix Curbot Bugs |  |  |  | Mike Sinn | 655.2378 |  |  | 1h 5m | 10h 21m | 4 | 5 | HIGH | CLOSED
2ftdw03 | Julia Lipton and CureDAO |  |  |  | Mike Sinn | 60.6701 |  |  | 1h 40m | 1h 40m | 4 | 5 | URGENT | CLOSED
2g4w281 | Evan Basson and CureDAO |  |  |  | Mike Sinn | 114.954 |  |  | 2h | 2h | 4 | 4 | URGENT | CLOSED
[5 empty] | Total: | 1240.4176
Lukas Vogel
Task ID | Task Name | Parent ID | Parent Name | Parent URL | Assignee | Bounty (formula) | TX URL (url) | Sent Tokens (currency) | Time Estimate | Time Logged | Urgency (1-5) (number) | Importance (1-5) (number) | Priority | Status
2k533vd | "Science bites" for constant social media presence |  |  |  | Lukas Vogel | 574.77 |  |  | 10h | 6h 57m | 4 | 4 |  | CLOSED
2k54cke | Create picture/figure templates to allow consistency | 2m7df6n | Create science bites for a test run (2 months; 2 posts a week) | https://app.clickup.com/t/2m7df6n | Lukas Vogel | 0 |  |  |  |  | 3 | 4 |  | CLOSED
2k54czq | Communicate the concept with the community and team regularly | 2m7df6n | Create science bites for a test run (2 months; 2 posts a week) | https://app.clickup.com/t/2m7df6n | Lukas Vogel | 0 |  |  |  |  | 3 | 4 |  | CLOSED
2k54dd5 | Get feedback/analyse community engagement with posts | 2m7df6n | Create science bites for a test run (2 months; 2 posts a week) | https://app.clickup.com/t/2m7df6n | Lukas Vogel | 0 |  |  |  |  | 3 | 4 |  | CLOSED
2k54z0g | Determine "hot topics" in search results / research to post CureDAO outcomes (like outcome labels) | 2k533vd | "Science bites" for constant social media presence | https://app.clickup.com/t/2k533vd | Lukas Vogel | 0 |  |  |  |  | 3 | 4 |  | CLOSED
2m7df6n | Create science bites for a test run (2 months; 2 posts a week) |  |  |  | Lukas Vogel | 574.77 |  |  | 10h | 7h 47m | 4 | 4 |  | CLOSED
2ftdw03 | Julia Lipton and CureDAO |  |  |  | Lukas Vogel | 60.6701 |  |  | 1h 40m | 1h 40m | 4 | 5 | URGENT | CLOSED
32b8e7z | Onboarding People & Organizational Work |  |  |  | Lukas Vogel | 582.3086 |  |  | 77h 37m | 77h 38m | 4 | 5 | URGENT | CLOSED
[5 empty] | Total: | 1792.5187
Lucas Jones
Task ID | Task Name | Parent ID | Parent Name | Parent URL | Assignee | Bounty (formula) | TX URL (url) | Sent Tokens (currency) | Time Estimate | Time Logged | Urgency (1-5) (number) | Importance (1-5) (number) | Priority | Status
2hywtcw | Represent Slide 1 in Figma: Title Page, Main Logo and Tagline | 2gwm004 | Add all PowerPoint slides to Figma => HTML => reusable blocks in WordPress or Webflow | https://app.clickup.com/t/2gwm004 | Lucas Jones | 101.1595 |  |  | 1h 6m | 1h 6m | 5 | 5 |  | CLOSED
2hywtfq | Represent Slide 2 in Figma: Symptom Severity | 2gwm004 | Add all PowerPoint slides to Figma => HTML => reusable blocks in WordPress or Webflow | https://app.clickup.com/t/2gwm004 | Lucas Jones | 0 |  |  |  |  | 5 | 5 |  | CLOSED
2hywtg9 | Represent Slide 3 in Figma: Cost of Research and What We Know | 2gwm004 | Add all PowerPoint slides to Figma => HTML => reusable blocks in WordPress or Webflow | https://app.clickup.com/t/2gwm004 | Lucas Jones | 0 |  |  |  |  | 5 | 5 |  | CLOSED
2hyua7y | Represent Slide 4 in Figma: Health Data and Innovation and Life Expectancy | 2gwm004 | Add all PowerPoint slides to Figma => HTML => reusable blocks in WordPress or Webflow | https://app.clickup.com/t/2gwm004 | Lucas Jones | 79.7014 |  |  | 52m | 52m | 5 | 5 |  | CLOSED
2hyxean | Represent Slide 5 in Figma: Horizontal Stagnation | 2gwm004 | Add all PowerPoint slides to Figma => HTML => reusable blocks in WordPress or Webflow | https://app.clickup.com/t/2gwm004 | Lucas Jones | 81.2342 |  |  | 53m | 54m | 5 | 5 |  | CLOSED
2hyxgwc | Represent Slide 6 in Figma: Thousands of Dashboards | 2gwm004 | Add all PowerPoint slides to Figma => HTML => reusable blocks in WordPress or Webflow | https://app.clickup.com/t/2gwm004 | Lucas Jones | 49.047 |  |  | 32m | 32m | 5 | 5 |  | CLOSED
2j4gm3n | Represent Slide 7 in Figma: Open-Source vs Closed-source, Accelerate Innovation | 2gwm004 | Add all PowerPoint slides to Figma => HTML => reusable blocks in WordPress or Webflow | https://app.clickup.com/t/2gwm004 | Lucas Jones | 41.3834 |  |  | 27m | 27m | 5 | 5 |  | CLOSED
2j4gvrm | Represent Slide 8 in Figma: The CureDAO Ecosystem | 2gwm004 | Add all PowerPoint slides to Figma => HTML => reusable blocks in WordPress or Webflow | https://app.clickup.com/t/2gwm004 | Lucas Jones | 84.2996 |  |  | 55m | 56m | 5 | 5 |  | CLOSED
2j4jrvj | Represent Slide 9 in Figma: Turning Oceans of Data into Precision Health | 2gwm004 | Add all PowerPoint slides to Figma => HTML => reusable blocks in WordPress or Webflow | https://app.clickup.com/t/2gwm004 | Lucas Jones | 24.5235 |  |  | 16m | 17m | 5 | 5 |  | CLOSED
2j4kmdx | Represent Slide 10 in Figma: Studies On Severity Metrics | 2gwm004 | Add all PowerPoint slides to Figma => HTML => reusable blocks in WordPress or Webflow | https://app.clickup.com/t/2gwm004 | Lucas Jones | 26.0562 |  |  | 17m | 18m | 5 | 5 |  | CLOSED
2j4krcr | Represent Slide 11 in Figma: Outcome Labels | 2gwm004 | Add all PowerPoint slides to Figma => HTML => reusable blocks in WordPress or Webflow | https://app.clickup.com/t/2gwm004 | Lucas Jones | 22.9908 |  |  | 15m | 15m | 5 | 5 |  | CLOSED
2jaae9d | Represent Slide 12 in Figma: Decision Support Notifications | 2gwm004 | Add all PowerPoint slides to Figma => HTML => reusable blocks in WordPress or Webflow | https://app.clickup.com/t/2gwm004 | Lucas Jones | 62.8415 |  |  | 41m | 41m | 5 | 5 |  | CLOSED
2jaazxh | Represent Slide 13 in Figma: Few Participants, Need More Input | 2gwm004 | Add all PowerPoint slides to Figma => HTML => reusable blocks in WordPress or Webflow | https://app.clickup.com/t/2gwm004 | Lucas Jones | 36.7853 |  |  | 24m | 25m | 5 | 5 |  | CLOSED
2jab417 | Represent Slide 14 in Figma: Wordpress: A Model for Open-Source Success | 2gwm004 | Add all PowerPoint slides to Figma => HTML => reusable blocks in WordPress or Webflow | https://app.clickup.com/t/2gwm004 | Lucas Jones | 42.9162 |  |  | 28m | 29m | 5 | 5 |  | CLOSED
2jabmxw | Represent Slide 15 in Figma: How It Works | 2gwm004 | Add all PowerPoint slides to Figma => HTML => reusable blocks in WordPress or Webflow | https://app.clickup.com/t/2gwm004 | Lucas Jones | 18.3926 |  |  | 12m | 13m | 5 | 5 |  | CLOSED
2jabtua | Represent Slide 16 in Figma: App Marketplace | 2gwm004 | Add all PowerPoint slides to Figma => HTML => reusable blocks in WordPress or Webflow | https://app.clickup.com/t/2gwm004 | Lucas Jones | 16.8599 |  |  | 11m | 11m | 5 | 5 |  | CLOSED
2jabuwq | Represent Slide 17 in Figma: Data Collection Plugins | 2gwm004 | Add all PowerPoint slides to Figma => HTML => reusable blocks in WordPress or Webflow | https://app.clickup.com/t/2gwm004 | Lucas Jones | 15.3272 |  |  | 10m | 10m | 5 | 5 |  | CLOSED
2jabwkw | Represent Slide 18 in Figma: Connector Plugins | 2gwm004 | Add all PowerPoint slides to Figma => HTML => reusable blocks in WordPress or Webflow | https://app.clickup.com/t/2gwm004 | Lucas Jones | 1.5327 |  |  | 1m | 2m | 5 | 5 |  | CLOSED
2jabz00 | Represent Slide 19 in Figma: Data Analysis Plugins | 2gwm004 | Add all PowerPoint slides to Figma => HTML => reusable blocks in WordPress or Webflow | https://app.clickup.com/t/2gwm004 | Lucas Jones | 4.5982 |  |  | 3m | 3m | 5 | 5 |  | CLOSED
2jabzf4 | Represent Slide 20 in Figma: Open Cures Trial Management Plugin | 2gwm004 | Add all PowerPoint slides to Figma => HTML => reusable blocks in WordPress or Webflow | https://app.clickup.com/t/2gwm004 | Lucas Jones | 29.1217 |  |  | 19m | 19m | 5 | 5 |  | CLOSED
2jac1au | Represent Slide 21 in Figma: Study Generation Plugins | 2gwm004 | Add all PowerPoint slides to Figma => HTML => reusable blocks in WordPress or Webflow | https://app.clickup.com/t/2gwm004 | Lucas Jones | 15.3272 |  |  | 10m | 10m | 5 | 5 |  | CLOSED
2jfz0rz | Represent Slide 22 in Figma: Zero Sum to Positive Sum | 2gwm004 | Add all PowerPoint slides to Figma => HTML => reusable blocks in WordPress or Webflow | https://app.clickup.com/t/2gwm004 | Lucas Jones | 16.8599 |  |  | 11m | 11m | 5 | 5 |  | CLOSED
2jfz7r5 | Represent Slide 23 in Figma: Intelligent Voluntary Cooperation | 2gwm004 | Add all PowerPoint slides to Figma => HTML => reusable blocks in WordPress or Webflow | https://app.clickup.com/t/2gwm004 | Lucas Jones | 96.5614 |  |  | 1h 3m | 1h 3m | 5 | 5 |  | CLOSED
2jg08da | Represent Slide 24 in Figma: User Segments | 2gwm004 | Add all PowerPoint slides to Figma => HTML => reusable blocks in WordPress or Webflow | https://app.clickup.com/t/2gwm004 | Lucas Jones | 44.4489 |  |  | 29m | 29m | 5 | 5 |  | CLOSED
2jg2ggx | Represent Slide 25 in Figma: Market Trends | 2gwm004 | Add all PowerPoint slides to Figma => HTML => reusable blocks in WordPress or Webflow | https://app.clickup.com/t/2gwm004 | Lucas Jones | 38.318 |  |  | 25m | 25m | 5 | 5 |  | CLOSED
2jg2q9b | Represent Slide 26 in Figma: B2B Data and SaaS Revenue | 2gwm004 | Add all PowerPoint slides to Figma => HTML => reusable blocks in WordPress or Webflow | https://app.clickup.com/t/2gwm004 | Lucas Jones | 42.9162 |  |  | 28m | 29m | 5 | 5 |  | CLOSED
2jg3919 | Represent Slide 27 in Figma: Benefits of a DAO | 2gwm004 | Add all PowerPoint slides to Figma => HTML => reusable blocks in WordPress or Webflow | https://app.clickup.com/t/2gwm004 | Lucas Jones | 42.9162 |  |  | 28m | 28m | 5 | 5 |  | CLOSED
2jg3d24 | Represent Slide 28 in Figma: Growth Strategy | 2gwm004 | Add all PowerPoint slides to Figma => HTML => reusable blocks in WordPress or Webflow | https://app.clickup.com/t/2gwm004 | Lucas Jones | 33.7198 |  |  | 22m | 23m | 5 | 5 |  | CLOSED
2jg3fq7 | Represent Slide 29 in Figma: Collaborators | 2gwm004 | Add all PowerPoint slides to Figma => HTML => reusable blocks in WordPress or Webflow | https://app.clickup.com/t/2gwm004 | Lucas Jones | 24.5235 |  |  | 16m | 16m | 5 | 5 |  | CLOSED
2jg3pum | Represent Slide 30 in Figma: Primary Market (Saas) | 2gwm004 | Add all PowerPoint slides to Figma => HTML => reusable blocks in WordPress or Webflow | https://app.clickup.com/t/2gwm004 | Lucas Jones | 15.3272 |  |  | 10m | 10m | 5 | 5 |  | CLOSED
2jg3rwz | Represent Slide 31 in Figma: U.S. Digital Health Market Chart | 2gwm004 | Add all PowerPoint slides to Figma => HTML => reusable blocks in WordPress or Webflow | https://app.clickup.com/t/2gwm004 | Lucas Jones | 6.1309 |  |  | 4m | 4m | 5 | 5 |  | CLOSED
2jg3u38 | Represent Slide 32 in Figma: Product Roadmap | 2gwm004 | Add all PowerPoint slides to Figma => HTML => reusable blocks in WordPress or Webflow | https://app.clickup.com/t/2gwm004 | Lucas Jones | 73.5706 |  |  | 48m | 49m | 5 | 5 |  | CLOSED
2jnt32y | Represent Slide 33 in Figma: Growth Roadmap | 2gwm004 | Add all PowerPoint slides to Figma => HTML => reusable blocks in WordPress or Webflow | https://app.clickup.com/t/2gwm004 | Lucas Jones | 87.365 |  |  | 57m | 58m | 5 | 5 |  | CLOSED
2jnt9ea | Represent Slide 34 in Figma: Current Collaborators | 2gwm004 | Add all PowerPoint slides to Figma => HTML => reusable blocks in WordPress or Webflow | https://app.clickup.com/t/2gwm004 | Lucas Jones | 22.9908 |  |  | 15m | 15m | 5 | 5 |  | CLOSED
2jnta3x | Represent Slide 35 in Figma: Use of Funds | 2gwm004 | Add all PowerPoint slides to Figma => HTML => reusable blocks in WordPress or Webflow | https://app.clickup.com/t/2gwm004 | Lucas Jones | 12.2618 |  |  | 8m | 8m | 5 | 5 |  | CLOSED
2jntaup | Represent Slide 36 in Figma: PEARL | 2gwm004 | Add all PowerPoint slides to Figma => HTML => reusable blocks in WordPress or Webflow | https://app.clickup.com/t/2gwm004 | Lucas Jones | 9.1963 |  |  | 6m | 7m | 5 | 5 |  | CLOSED
2jntb50 | Represent Slide 37 in Figma: Stopping Alzheimer's | 2gwm004 | Add all PowerPoint slides to Figma => HTML => reusable blocks in WordPress or Webflow | https://app.clickup.com/t/2gwm004 | Lucas Jones | 9.1963 |  |  | 6m | 6m | 5 | 5 |  | CLOSED
2jntded | Represent Slide 38 in Figma: Annual Expenses | 2gwm004 | Add all PowerPoint slides to Figma => HTML => reusable blocks in WordPress or Webflow | https://app.clickup.com/t/2gwm004 | Lucas Jones | 10.729 |  |  | 7m | 7m | 5 | 5 |  | CLOSED
2jntera | Represent Slide 39 in Figma: Binance Launchpad | 2gwm004 | Add all PowerPoint slides to Figma => HTML => reusable blocks in WordPress or Webflow | https://app.clickup.com/t/2gwm004 | Lucas Jones | 10.729 |  |  | 7m | 7m | 5 | 5 |  | CLOSED
2jntev5 | Represent Slide 40 in Figma: Tokenomics | 2gwm004 | Add all PowerPoint slides to Figma => HTML => reusable blocks in WordPress or Webflow | https://app.clickup.com/t/2gwm004 | Lucas Jones | 7.6636 |  |  | 5m | 5m | 5 | 5 |  | CLOSED
2jntfcd | Represent Slide 41 in Figma: Contributors | 2gwm004 | Add all PowerPoint slides to Figma => HTML => reusable blocks in WordPress or Webflow | https://app.clickup.com/t/2gwm004 | Lucas Jones | 55.1779 |  |  | 36m | 36m | 5 | 5 |  | CLOSED
2jntkr8 | Represent Slide 42 in Figma: Advisory Board | 2gwm004 | Add all PowerPoint slides to Figma => HTML => reusable blocks in WordPress or Webflow | https://app.clickup.com/t/2gwm004 | Lucas Jones | 53.6452 |  |  | 35m | 36m | 5 | 5 |  | CLOSED
2jntn1d | Represent Slide 43 in Figma: Empty Slide | 2gwm004 | Add all PowerPoint slides to Figma => HTML => reusable blocks in WordPress or Webflow | https://app.clickup.com/t/2gwm004 | Lucas Jones | 0.7664 |  |  | 1m |  | 5 | 5 |  | CLOSED
2jntn2a | Represent Slide 44 in Figma: Appendix | 2gwm004 | Add all PowerPoint slides to Figma => HTML => reusable blocks in WordPress or Webflow | https://app.clickup.com/t/2gwm004 | Lucas Jones | 1.5327 |  |  | 1m | 2m | 5 | 5 |  | CLOSED
2jntn6u | Represent Slide 45 in Figma: Business Validation | 2gwm004 | Add all PowerPoint slides to Figma => HTML => reusable blocks in WordPress or Webflow | https://app.clickup.com/t/2gwm004 | Lucas Jones | 9.1963 |  |  | 6m | 6m | 5 | 5 |  | CLOSED
2jnv8d0 | Represent Slide 46 in Figma: Current Total Addressable Market | 2gwm004 | Add all PowerPoint slides to Figma => HTML => reusable blocks in WordPress or Webflow | https://app.clickup.com/t/2gwm004 | Lucas Jones | 10.729 |  |  | 7m | 7m | 5 | 5 |  | CLOSED
2jnv8x1 | Represent Slide 47 in Figma: SaaS Pricing | 2gwm004 | Add all PowerPoint slides to Figma => HTML => reusable blocks in WordPress or Webflow | https://app.clickup.com/t/2gwm004 | Lucas Jones | 12.2618 |  |  | 8m | 8m | 5 | 5 |  | CLOSED
2jnv9ae | Represent Slide 48 in Figma: Legal Structures | 2gwm004 | Add all PowerPoint slides to Figma => HTML => reusable blocks in WordPress or Webflow | https://app.clickup.com/t/2gwm004 | Lucas Jones | 27.589 |  |  | 18m | 18m | 5 | 5 |  | CLOSED
2jnva3e | Represent Slide 49 in Figma: CureDAO Platform Architecture | 2gwm004 | Add all PowerPoint slides to Figma => HTML => reusable blocks in WordPress or Webflow | https://app.clickup.com/t/2gwm004 | Lucas Jones | 45.9816 |  |  | 30m | 30m | 5 | 5 |  | CLOSED
2jnvv12 | Represent Slide 50 in Figma: Causal Relationships | 2gwm004 | Add all PowerPoint slides to Figma => HTML => reusable blocks in WordPress or Webflow | https://app.clickup.com/t/2gwm004 | Lucas Jones | 9.1963 |  |  | 6m | 6m | 5 | 5 |  | CLOSED
2jnvv8g | Represent Slide 51 in Figma: Decentralized Exchange IDOs | 2gwm004 | Add all PowerPoint slides to Figma => HTML => reusable blocks in WordPress or Webflow | https://app.clickup.com/t/2gwm004 | Lucas Jones | 13.7945 |  |  | 9m | 9m | 5 | 5 |  | CLOSED
2jnvvqj | Represent Slide 52 in Figma: Links | 2gwm004 | Add all PowerPoint slides to Figma => HTML => reusable blocks in WordPress or Webflow | https://app.clickup.com/t/2gwm004 | Lucas Jones | 12.2618 |  |  | 8m | 8m | 5 | 5 |  | CLOSED
2jnvw1c | Represent Slide 53 in Figma: Alternative Problem Statement | 2gwm004 | Add all PowerPoint slides to Figma => HTML => reusable blocks in WordPress or Webflow | https://app.clickup.com/t/2gwm004 | Lucas Jones | 7.6636 |  |  | 5m | 5m | 5 | 5 |  | CLOSED
2jnvwb8 | Represent Slide 54 in Figma: CureDAO End Slogan | 2gwm004 | Add all PowerPoint slides to Figma => HTML => reusable blocks in WordPress or Webflow | https://app.clickup.com/t/2gwm004 | Lucas Jones | 26.0562 |  |  | 17m | 17m | 5 | 5 |  | CLOSED
Keith Comito |  |  |  |  | Total: | 1645.3748
Task ID | Task Name | Parent ID | Parent Name | Parent URL | Assignee | Bounty (formula) | TX URL (url) | Sent Tokens (currency) | Time Estimate | Time Logged | Urgency (1-5) (number) | Importance (1-5) (number) | Priority | Status
2jnvpu6 | Ongoing conversations w/ day job re: integrating biomarker systems with systems like CureDAO and creating connection points |  |  |  | Keith Comito | 145.6084 |  |  | 2h | 2h | 4 | 5 |  | CLOSED [WON]
Andreas Melhede |  |  |  |  | Total: | 145.6084
Task ID | Task Name | Parent ID | Parent Name | Parent URL | Assignee | Bounty (formula) | TX URL (url) | Sent Tokens (currency) | Time Estimate | Time Logged | Urgency (1-5) (number) | Importance (1-5) (number) | Priority | Status
2r6nbwn | Send The Compensation to the rest of the contributors prior to using ClickUp |  |  |  | Andreas Melhede | 145.6084 |  |  | 1h 35m | 1h 36m | 5 | 5 | URGENT | CLOSED
2ct7yuk | Add to Discord Labs | 2ct7yue | Darren Nesbeth | https://app.clickup.com/t/2ct7yue | Andreas Melhede | 0 | [7 empty] | CLOSED
2ct7yun | Add their weekly available hours here: https://app.clickup.com/10641228/v/wl/a4quc-13140 | 2ct7yue | Darren Nesbeth | https://app.clickup.com/t/2ct7yue | Andreas Melhede | 0 | [7 empty] | CLOSED
2dv4bz1 | Schedule an onboarding call | 2dv4byx | Tovah | https://app.clickup.com/t/2dv4byx | Andreas Melhede | 0 | [7 empty] | CLOSED
2dv4bz2 | Invite and add to appropriate GitHub teams | 2dv4byx | Tovah | https://app.clickup.com/t/2dv4byx | Andreas Melhede | 0 | [7 empty] | CLOSED
2dv4bz3 | Add "Design Lab" members to the "CureDAO Design Team" in Figma | 2dv4byx | Tovah | https://app.clickup.com/t/2dv4byx | Andreas Melhede | 0 | [7 empty] | CLOSED
2dv4bz4 | Add to Discord Labs | 2dv4byx | Tovah | https://app.clickup.com/t/2dv4byx | Andreas Melhede | 0 | [7 empty] | CLOSED
2dv4bz6 | Add their weekly available hours here: https://app.clickup.com/10641228/v/wl/a4quc-13140 | 2dv4byx | Tovah | https://app.clickup.com/t/2dv4byx | Andreas Melhede | 0 | [7 empty] | CLOSED
30qnzp4 | Add to Clickup, make them guests, create onboarding tasks for them, and grant them access to their onboarding tasks | 30qnzne | Marcellus Simon | https://app.clickup.com/t/30qnzne | Andreas Melhede | 0 | [7 empty] | CLOSED
30qv06y | Add to Clickup, make them guests, create onboarding tasks for them, and grant them access to their onboarding tasks | 30qv06r | Samuel Akio | https://app.clickup.com/t/30qv06r | Andreas Melhede | 0 | [7 empty] | CLOSED
2dm0mnk | Schedule an onboarding call | 2dm0mne | Maulik M Dhandha | https://app.clickup.com/t/2dm0mne | Andreas Melhede | 0 | [7 empty] | CLOSED
2f3ea3h | Schedule an onboarding call | 2f3ea3a | Richard Sprague | https://app.clickup.com/t/2f3ea3a | Andreas Melhede | 0 | [7 empty] | CLOSED
2gpphv5 | Schedule an onboarding call | 2gpphub | Jiré Saffron | https://app.clickup.com/t/2gpphub | Andreas Melhede | 0 | [7 empty] | CLOSED
31ere2x | Add to Clickup, make them guests, create onboarding tasks for them, and grant them access to their onboarding tasks | 31ere2e | Moses | https://app.clickup.com/t/31ere2e | Andreas Melhede | 0 | [7 empty] | CLOSED
31mghk6 | Compensate people with tokens |  |  |  | Andreas Melhede | 113.4213 |  |  | 1h 14m | 1h 14m | 5 | 5 | URGENT | CLOSED
2hkb02t | Add their weekly available hours here: https://app.clickup.com/10641228/v/wl/a4quc-13140 | 2hkb02h | Lucas Jones | https://app.clickup.com/t/2hkb02h | Andreas Melhede | 0 | [7 empty] | CLOSED
2pjj0h0 | Send 10 $CURE1 Tokens & let them know | 2pjj0gz | Soya Oda | https://app.clickup.com/t/2pjj0gz | Andreas Melhede | 0 | [7 empty] | CLOSED
32b8ek1 | Check on deadlines for tasks |  |  |  | Andreas Melhede | 10.729 |  |  | 7m | 8m | 5 | 5 | URGENT | CLOSED
32h0ax0 | Check on deadlines for tasks |  |  |  | Andreas Melhede | 16.8599 |  |  | 11m | 11m | 5 | 5 | URGENT | CLOSED
32h0j0z | Update Orbit Discord integration |  |  |  | Andreas Melhede | 0 |  |  | 1m |  | 4 | 4 | HIGH | CLOSED
2hdv5c5 | Send 10 $CURE1 Tokens & let them know | 2hdv5bj | Evan Basson AKA MotionFactory | https://app.clickup.com/t/2hdv5bj | Andreas Melhede | 0 | [7 empty] | CLOSED
32pn76c | Update Orbit Discord integration |  |  |  | Andreas Melhede | 0 |  |  | 1m |  | 4 | 4 | HIGH | CLOSED
32pn8xx | Check on deadlines for tasks |  |  |  | Andreas Melhede | 0 |  |  |  |  | 5 | 5 | URGENT | CLOSED
32w9h7z | Update Orbit Discord integration |  |  |  | Andreas Melhede | 0 |  |  | 1m |  | 4 | 4 | HIGH | CLOSED
2jfxr1p | Add to Clickup, make them guests, create onboarding tasks for them, and grant them access to their onboarding tasks | 2jfxr08 | Mike Hollen | https://app.clickup.com/t/2jfxr08 | Andreas Melhede | 0 | [7 empty] | CLOSED
32b8e7z | Onboarding People & Organizational Work |  |  |  | Andreas Melhede | 5068.5107 |  |  | 77h 37m | 77h 38m | 4 | 5 | URGENT | CLOSED
[5 empty] | Total: | 5355.1293