## Tasks
Mike Sinn
Task ID | Task Name | Parent ID | Parent Name | Parent URL | Assignee | Bounty (formula) | TX URL (url) | Sent Tokens (currency) | Time Estimate | Time Logged | Urgency (1-5) (number) | Importance (1-5) (number) | Priority | Status
2yruq50 | DAO Multisig-Wallet For crowdfunding |  |  |  | Mike Sinn | 36.4021 |  |  | 30m |  | 4 | 5 |  | CLOSED
2vdfep6 | How many total customers or users (as applicable) did your company have over the last six months? Please break down the number by month |  |  |  | Mike Sinn | 183.9264 |  |  | 2h | 2h | 5 | 5 | URGENT | CLOSED
2e5rvw5 | Uche James and CureDAO |  |  |  | Mike Sinn | 36.4021 |  |  | 30m |  | 5 | 4 | URGENT | CLOSED
27wwhw9 | About Us Narrative |  |  |  | Mike Sinn | 99.6268 |  |  | 1h 5m | 1h 9m | 5 | 5 |  | CLOSED
2d97590 | Add "Design Lab" members to the "CureDAO Design Team" in Figma | 2d9758v | Noah Weber | https://app.clickup.com/t/2d9758v | Mike Sinn | 9.1963 |  |  | 6m |  | 5 | 5 |  | CLOSED
3an4ujy | Daily Scrum Meeting (Mike) |  |  |  | Mike Sinn | 66.7372 |  |  | 55m |  | 4 | 5 |  | CLOSED
3b0f42x | Daily Scrum Meeting (Mike) |  |  |  | Mike Sinn | 66.7372 |  |  | 55m |  | 4 | 5 |  | CLOSED
2epv22j | Olanrewaju Magbagbeola and CureDAO |  |  |  | Mike Sinn | 36.4021 |  |  | 30m |  | 5 | 4 | URGENT | CLOSED
3bhm8jm | Daily Scrum Meeting (Mike) |  |  |  | Mike Sinn | 66.7372 |  |  | 55m | 1h | 4 | 5 |  | CLOSED
Lukas Vogel |  |  |  |  | Total: | 602.1674
Task ID | Task Name | Parent ID | Parent Name | Parent URL | Assignee | Bounty (formula) | TX URL (url) | Sent Tokens (currency) | Time Estimate | Time Logged | Urgency (1-5) (number) | Importance (1-5) (number) | Priority | Status
2deadp1 | Onboarding Task |  |  |  | Lukas Vogel | 0 |  |  |  | 10m |  |  | URGENT | COMPLETE
2deadp3 | Organizing with the Hierarchy | 2deadp1 | Onboarding Task | https://app.clickup.com/t/2deadp1 | Lukas Vogel | 1.3411 |  |  | 3m |  | 2 | 4 | NORMAL | COMPLETE
2deadp4 | Filter and sort your tasks | 2deadp1 | Onboarding Task | https://app.clickup.com/t/2deadp1 | Lukas Vogel | 1.3411 |  |  | 3m |  | 2 | 4 | NORMAL | COMPLETE
2deadp5 | Task Statuses and Priorities | 2deadp1 | Onboarding Task | https://app.clickup.com/t/2deadp1 | Lukas Vogel | 2.6823 |  |  | 3m |  | 3 | 5 | HIGH | COMPLETE
2deadp6 | Setting due dates to keep your team on track | 2deadp1 | Onboarding Task | https://app.clickup.com/t/2deadp1 | Lukas Vogel | 6.2586 |  |  | 7m |  | 3 | 5 | URGENT | COMPLETE
2deadp7 | Home and Prioritizing your team's tasks | 2deadp1 | Onboarding Task | https://app.clickup.com/t/2deadp1 | Lukas Vogel | 4.4704 |  |  | 5m |  | 3 | 5 | HIGH | COMPLETE
2deadp8 | Collaborating with tasks | 2deadp1 | Onboarding Task | https://app.clickup.com/t/2deadp1 | Lukas Vogel | 0.6386 |  |  | 5m |  | 1 | 3 | LOW | COMPLETE
2deadp9 | Recurring tasks: this task will restart when closed | 2deadp1 | Onboarding Task | https://app.clickup.com/t/2deadp1 | Lukas Vogel | 0.8941 |  |  | 2m |  | 2 | 4 | NORMAL | COMPLETE
2deadpb | Managing ClickUp Notifications | 2deadp1 | Onboarding Task | https://app.clickup.com/t/2deadp1 | Lukas Vogel | 1.3411 |  |  | 3m |  | 2 | 4 | HIGH | COMPLETE
2deadpc | Communication with your team in ClickUp | 2deadp1 | Onboarding Task | https://app.clickup.com/t/2deadp1 | Lukas Vogel | 2.2352 |  |  | 5m |  | 2 | 4 | LOW | COMPLETE
2deadpd | Weekly Team Goals | 2deadp1 | Onboarding Task | https://app.clickup.com/t/2deadp1 | Lukas Vogel | 0.3832 |  |  | 3m |  | 1 | 3 | LOW | COMPLETE
2deadpe | Save your team time with reusable templates! | 2deadp1 | Onboarding Task | https://app.clickup.com/t/2deadp1 | Lukas Vogel | 2.6823 |  |  | 3m |  | 3 | 5 | HIGH | COMPLETE
2deadpg | Custom Fields | 2deadp1 | Onboarding Task | https://app.clickup.com/t/2deadp1 | Lukas Vogel | 3.1293 |  |  | 7m |  | 2 | 4 | NORMAL | COMPLETE
2deadpj | Dashboards at a high level to measure your team's progress | 2deadp1 | Onboarding Task | https://app.clickup.com/t/2deadp1 | Lukas Vogel | 3.1293 |  |  | 7m |  | 2 | 4 | NORMAL | COMPLETE
2deadpm | Disable Hot Keys for Better Linking to Documents | 2deadp1 | Onboarding Task | https://app.clickup.com/t/2deadp1 | Lukas Vogel | 1.3411 |  |  | 3m |  | 2 | 4 | NORMAL | COMPLETE
2deadpn | ClickUp Views | 2deadp1 | Onboarding Task | https://app.clickup.com/t/2deadp1 | Lukas Vogel | 0.6386 |  |  | 5m |  | 1 | 3 | LOW | COMPLETE
2deadpq | The ClickUp Chrome Extension | 2deadp1 | Onboarding Task | https://app.clickup.com/t/2deadp1 | Lukas Vogel | 2.2352 |  |  | 5m |  | 2 | 4 | NORMAL | COMPLETE
2deadpr | How to make social media posts for CureDAO | 2deadp1 | Onboarding Task | https://app.clickup.com/t/2deadp1 | Lukas Vogel | 1.3411 |  |  | 3m |  | 2 | 4 | NORMAL | COMPLETE
2deadpu | How To Reduce Discord Notifications | 2deadp1 | Onboarding Task | https://app.clickup.com/t/2deadp1 | Lukas Vogel | 0.8941 |  |  | 3m |  | 2 | 4 | NORMAL | COMPLETE
2deadpw | Add CureDAO's Calendar to Google Calendar | 2deadp1 | Onboarding Task | https://app.clickup.com/t/2deadp1 | Lukas Vogel | 8.9409 |  |  | 1m |  | 3 | 5 | HIGH | COMPLETE
2deadpx | Add $GCURES to MetaMask | 2deadp1 | Onboarding Task | https://app.clickup.com/t/2deadp1 | Lukas Vogel | 3.6402 |  |  | 10m |  | 3 | 5 | HIGH | COMPLETE
2deadq0 | Schedule a call to find your first quest and get started! | 2deadp1 | Onboarding Task | https://app.clickup.com/t/2deadp1 | Lukas Vogel | 3.6402 |  |  | 3m |  | 4 | 5 | URGENT | COMPLETE
2deadq3 | Do this last: How would you improve the onboarding process? | 2deadp1 | Onboarding Task | https://app.clickup.com/t/2deadp1 | Lukas Vogel | 10.9206 |  |  | 9m |  | 4 | 5 | HIGH | COMPLETE
Keith Comito |  |  |  |  | Total: | 64.1186
Task ID | Task Name | Parent ID | Parent Name | Parent URL | Assignee | Bounty (formula) | TX URL (url) | Sent Tokens (currency) | Time Estimate | Time Logged | Urgency (1-5) (number) | Importance (1-5) (number) | Priority | Status
2fu6bwn | Added discussion of CureDAO into forthcoming book Geroscience: A New Frontier in Public Health (Cold Spring Harbor Laboratory Press, 2022) |  |  |  | Keith Comito | 145.6084 |  |  | 2h | 2h | 4 | 5 |  | CLOSED [WON]
2fzy150 | Discussion with VC Fund at QuadraScope; interested in learning more / potentially investing -> connected w/ Mike S. |  |  |  | Keith Comito | 145.6084 |  |  | 2h | 2h | 5 | 4 |  | CLOSED [WON]
Ekene Umeh |  |  |  |  | Total: | 291.2168
Task ID | Task Name | Parent ID | Parent Name | Parent URL | Assignee | Bounty (formula) | TX URL (url) | Sent Tokens (currency) | Time Estimate | Time Logged | Urgency (1-5) (number) | Importance (1-5) (number) | Priority | Status
2vrwghw | Organizing with the Hierarchy | 2vrwghu | Onboarding Task | https://app.clickup.com/t/2vrwghu | Ekene Umeh | 1.3411 |  |  | 3m |  | 2 | 4 | NORMAL | COMPLETE
2vrwghy | Filter and sort your tasks | 2vrwghu | Onboarding Task | https://app.clickup.com/t/2vrwghu | Ekene Umeh | 1.3411 |  |  | 3m |  | 2 | 4 | NORMAL | COMPLETE
2vrwghz | Task Statuses and Priorities | 2vrwghu | Onboarding Task | https://app.clickup.com/t/2vrwghu | Ekene Umeh | 2.6823 |  |  | 3m |  | 3 | 5 | HIGH | COMPLETE
2vrwgj0 | Setting due dates to keep your team on track | 2vrwghu | Onboarding Task | https://app.clickup.com/t/2vrwghu | Ekene Umeh | 6.2586 |  |  | 7m |  | 3 | 5 | URGENT | COMPLETE
2vrwgj1 | Home and Prioritizing your team's tasks | 2vrwghu | Onboarding Task | https://app.clickup.com/t/2vrwghu | Ekene Umeh | 4.4704 |  |  | 5m |  | 3 | 5 | HIGH | COMPLETE
2vrwgj2 | Collaborating with tasks | 2vrwghu | Onboarding Task | https://app.clickup.com/t/2vrwghu | Ekene Umeh | 0.6386 |  |  | 5m |  | 1 | 3 | LOW | COMPLETE
2vrwgj4 | Recurring tasks: this task will restart when closed | 2vrwghu | Onboarding Task | https://app.clickup.com/t/2vrwghu | Ekene Umeh | 0.8941 |  |  | 2m |  | 2 | 4 | NORMAL | COMPLETE
2vrwgj6 | Managing ClickUp Notifications | 2vrwghu | Onboarding Task | https://app.clickup.com/t/2vrwghu | Ekene Umeh | 1.3411 |  |  | 3m |  | 2 | 4 | HIGH | COMPLETE
2vrwgj7 | Communication with your team in ClickUp | 2vrwghu | Onboarding Task | https://app.clickup.com/t/2vrwghu | Ekene Umeh | 2.2352 |  |  | 5m |  | 2 | 4 | LOW | COMPLETE
2vrwgj8 | Weekly Team Goals | 2vrwghu | Onboarding Task | https://app.clickup.com/t/2vrwghu | Ekene Umeh | 0.3832 |  |  | 3m |  | 1 | 3 | LOW | COMPLETE
2vrwgj9 | Save your team time with reusable templates! | 2vrwghu | Onboarding Task | https://app.clickup.com/t/2vrwghu | Ekene Umeh | 2.6823 |  |  | 3m |  | 3 | 5 | HIGH | COMPLETE
2vrwgjb | Custom Fields | 2vrwghu | Onboarding Task | https://app.clickup.com/t/2vrwghu | Ekene Umeh | 3.1293 |  |  | 7m |  | 2 | 4 | NORMAL | COMPLETE
2vrwgjc | Dashboards at a high level to measure your team's progress | 2vrwghu | Onboarding Task | https://app.clickup.com/t/2vrwghu | Ekene Umeh | 3.1293 |  |  | 7m |  | 2 | 4 | NORMAL | COMPLETE
2vrwgjd | Disable Hot Keys for Better Linking to Documents | 2vrwghu | Onboarding Task | https://app.clickup.com/t/2vrwghu | Ekene Umeh | 1.3411 |  |  | 3m |  | 2 | 4 | NORMAL | COMPLETE
2vrwgje | ClickUp Views | 2vrwghu | Onboarding Task | https://app.clickup.com/t/2vrwghu | Ekene Umeh | 0.6386 |  |  | 5m |  | 1 | 3 | LOW | COMPLETE
2vrwgjg | The ClickUp Chrome Extension | 2vrwghu | Onboarding Task | https://app.clickup.com/t/2vrwghu | Ekene Umeh | 2.2352 |  |  | 5m |  | 2 | 4 | NORMAL | COMPLETE
2vrwgjh | How to make social media posts for CureDAO | 2vrwghu | Onboarding Task | https://app.clickup.com/t/2vrwghu | Ekene Umeh | 1.3411 |  |  | 3m |  | 2 | 4 | NORMAL | COMPLETE
2vrwgjm | How To Reduce Discord Notifications | 2vrwghu | Onboarding Task | https://app.clickup.com/t/2vrwghu | Ekene Umeh | 1.3411 |  |  | 3m |  | 2 | 4 | NORMAL | COMPLETE
2vrwgjn | Add CureDAO's Calendar to Google Calendar | 2vrwghu | Onboarding Task | https://app.clickup.com/t/2vrwghu | Ekene Umeh | 0.8941 |  |  | 1m |  | 3 | 5 | HIGH | COMPLETE
2vrwgjp | Add $GCURES to MetaMask | 2vrwghu | Onboarding Task | https://app.clickup.com/t/2vrwghu | Ekene Umeh | 8.9409 |  |  | 10m |  | 3 | 5 | HIGH | COMPLETE
2vrwgjq | Schedule a call to find your first quest and get started! | 2vrwghu | Onboarding Task | https://app.clickup.com/t/2vrwghu | Ekene Umeh | 3.6402 |  |  | 3m |  | 4 | 5 | URGENT | COMPLETE
2vrwgjr | Do this last: How would you improve the onboarding process? | 2vrwghu | Onboarding Task | https://app.clickup.com/t/2vrwghu | Ekene Umeh | 10.9206 |  |  | 9m |  | 4 | 5 | HIGH | COMPLETE
2vrwghu | Onboarding Task |  |  |  | Ekene Umeh | 0 | [6 empty] | HIGH | COMPLETE
Andreas Melhede |  |  |  |  | Total: | 61.8195
Task ID | Task Name | Parent ID | Parent Name | Parent URL | Assignee | Bounty (formula) | TX URL (url) | Sent Tokens (currency) | Time Estimate | Time Logged | Urgency (1-5) (number) | Importance (1-5) (number) | Priority | Status
2t33jm3 | Compensate people with tokens |  |  |  | Andreas Melhede | 202.319 |  |  | 2h 12m | 2h 13m | 5 | 5 | URGENT | CLOSED
2yrxvqk | Send 10 $CURE1 Tokens & let them know | 2yrxvqj | Prince Uche | https://app.clickup.com/t/2yrxvqj | Andreas Melhede | 0 | [7 empty] | CLOSED
2yrxvqm | Schedule an onboarding call | 2yrxvqj | Prince Uche | https://app.clickup.com/t/2yrxvqj | Andreas Melhede | 0 | [7 empty] | CLOSED
2yykfzq | Schedule an onboarding call | 2yykfzk | Ken | https://app.clickup.com/t/2yykfzk | Andreas Melhede | 0 | [7 empty] | CLOSED
2yykg00 | Add to Clickup, make them guests, create onboarding tasks for them, and grant them access to their onboarding tasks | 2yykfzk | Ken | https://app.clickup.com/t/2yykfzk | Andreas Melhede | 0 | [7 empty] | CLOSED
25cwkp6 | 500 Global Flagship Accelerator Program |  |  |  | Andreas Melhede | 406.1708 |  |  | 4h 25m | 4h 25m | 5 | 5 | HIGH | CLOSED [WON]
2vk4y29 | Update Orbit Discord integration |  |  |  | Andreas Melhede | 0.958 |  |  | 1m |  | 4 | 4 | HIGH | CLOSED
2vk4y32 | Onboarding People & Organizational Work |  |  |  | Andreas Melhede | 531.4707 |  |  | 7h 18m | 7h 19m | 4 | 5 | URGENT | CLOSED
2vk4y52 | Check on deadlines for tasks |  |  |  | Andreas Melhede | 3.0654 |  |  | 2m | 3m | 5 | 5 | URGENT | CLOSED
2vk7rbb | Update Orbit Discord integration |  |  |  | Andreas Melhede | 0.958 |  |  | 1m |  | 4 | 4 | HIGH | CLOSED
2vk7rdk | Onboarding People & Organizational Work |  |  |  | Andreas Melhede | 461.0933 |  |  | 6h 20m | 6h 20m | 4 | 5 | URGENT | CLOSED
2vk7rqb | Check on deadlines for tasks |  |  |  | Andreas Melhede | 3.0654 |  |  | 2m | 4m | 5 | 5 | URGENT | CLOSED
2vk8dx7 | Analyze Binance Launchpad & Launchpool Sale - Application criteria |  |  |  | Andreas Melhede | 105.7577 |  |  | 1h 9m | 1h 9m | 5 | 5 | URGENT | CLOSED
2vkc9tu | Update Orbit Discord integration |  |  |  | Andreas Melhede | 0.958 |  |  | 1m |  | 4 | 4 | HIGH | CLOSED
2vkcdcg | Onboarding People & Organizational Work |  |  |  | Andreas Melhede | 389.5025 |  |  | 5h 21m | 5h 22m | 4 | 5 | URGENT | CLOSED
2vkcdxd | Check on deadlines for tasks |  |  |  | Andreas Melhede | 10.729 |  |  | 7m | 7m | 5 | 5 | URGENT | CLOSED
2zfump4 | Send 10 $CURE1 Tokens & let them know | 2zfump1 | Andrea Maggetto | https://app.clickup.com/t/2zfump1 | Andreas Melhede | 0 | [7 empty] | CLOSED
2zfumpp | Add to Clickup, make them guests, create onboarding tasks for them, and grant them access to their onboarding tasks | 2zfump1 | Andrea Maggetto | https://app.clickup.com/t/2zfump1 | Andreas Melhede | 0 | [7 empty] | CLOSED
2vt2dc0 | Onboarding People & Organizational Work |  |  |  | Andreas Melhede | 1932.9515 |  |  | 26h 33m | 26h 33m | 4 | 5 | URGENT | CLOSED
[5 empty] | Total: | 4048.9993