## Tasks
Vincenzo Domina
Task ID | Task Name | Parent ID | Parent Name | Parent URL | Assignee | Bounty (formula) | TX URL (url) | Sent Tokens (currency) | Time Estimate | Time Logged | Urgency (1-5) (number) | Importance (1-5) (number) | Priority | Status
2r6mhb0 | BioViva post on social channels |  |  |  | Vincenzo Domina | 19.159 |  |  | 20m |  | 4 | 4 |  | CLOSED
2f1pxac | Sign this petition against the FDA! IF WE DO NOT TREAT THE CAUSE, WE WILL SUFFER THE EFFECT. |  |  |  | Vincenzo Domina | 28.7385 |  |  | 30m | 20m | 4 | 4 |  | CLOSED
26b93c2 | Optimize The "Get Started Here" Channel |  |  |  | Mike Sinn, Vincenzo Domina | 91.9632 |  |  | 1h 30m | 1h | 5 | 5 | HIGH | CLOSED
Mike Sinn |  |  |  |  | Total: | 139.8607
Task ID | Task Name | Parent ID | Parent Name | Parent URL | Assignee | Bounty (formula) | TX URL (url) | Sent Tokens (currency) | Time Estimate | Time Logged | Urgency (1-5) (number) | Importance (1-5) (number) | Priority | Status
2nw4zgw | Weekly Planning Meeting (Mike) |  |  |  | Mike Sinn | 367.8528 |  |  | 4h |  | 5 | 5 |  | CLOSED
29wkeht | Call Starring Stephanie Dainow! :D |  |  |  | Mike Sinn | 114.954 |  |  | 2h |  | 4 | 4 | URGENT | CLOSED
2a7vq25 | Emmanuel Agboola and CureDAO |  |  |  | Mike Sinn | 42.1498 |  |  | 1h |  | 3 | 4 | URGENT | CLOSED
2a7zfpc | Andre Chagwedera and CureDAO |  |  |  | Mike Sinn | 72.8042 |  |  | 1h |  | 4 | 5 | URGENT | CLOSED
2adqupa | Brad English and CureDAO |  |  |  | Mike Sinn | 21.0749 |  |  | 30m |  | 3 | 4 | URGENT | CLOSED
2cjaup5 | Fer Zager and CureDAO |  |  |  | Mike Sinn | 57.477 |  |  | 1h |  | 4 | 4 | URGENT | CLOSED
2cjbefh | Database Schema, scrum, and organizational calls |  |  |  | Mike Sinn | 194.1445 |  |  | 2h 40m |  | 4 | 5 | URGENT | CLOSED
2acybyn | Consider Próspera Incorporation |  |  |  | Mike Sinn | 68.9724 |  |  | 45m |  | 5 | 5 |  | CLOSED
2cr2g63 | Mark Melnykowycz and CureDAO |  |  |  | Mike Sinn | 91.9632 |  |  | 1h |  | 5 | 5 | URGENT | CLOSED
2cr3fcz | Komal Jain and CureDAO |  |  |  | Mike Sinn | 72.8042 |  |  | 1h |  | 4 | 5 | URGENT | CLOSED
2cr5a0p | Jesse Uche and CureDAO |  |  |  | Mike Sinn | 72.8042 |  |  | 1h |  | 4 | 5 | URGENT | CLOSED
2cxq4wr | Derek Underwood and CureDAO |  |  |  | Mike Sinn | 53.6452 |  |  | 35m |  | 5 | 5 | URGENT | CLOSED
2cxq8r7 | Intros Rich <> Vincenzo and Mike |  |  |  | Mike Sinn | 72.8042 |  |  | 1h |  | 4 | 5 | URGENT | CLOSED
2y7tjx1 | Add to Clickup, make them guests, create onboarding tasks for them, and grant them access to their onboarding tasks | 2y7tjwu | Richard Maraschi | https://app.clickup.com/t/2y7tjwu | Mike Sinn | 7.6636 |  |  | 5m |  | 5 | 5 |  | CLOSED
26b93c2 | Optimize The "Get Started Here" Channel |  |  |  | Mike Sinn, Vincenzo Domina | 45.9816 |  |  | 1h 30m | 30m | 5 | 5 | HIGH | CLOSED
2kqjyku | Determine The Compensation for the rest of the people prior to using ClickUp |  |  |  | Mike Sinn, Andreas Melhede | 72.8042 |  |  | 2h | 1h | 4 | 5 | HIGH | CLOSED
2n5b36q | Finalize DeSciWorld Application |  |  |  | Andreas Melhede, Mike Sinn | 91.0053 |  |  | 1h 15m |  | 4 | 5 | HIGH | CLOSED
Keith Comito |  |  |  |  | Total: | 1520.9053
Task ID | Task Name | Parent ID | Parent Name | Parent URL | Assignee | Bounty (formula) | TX URL (url) | Sent Tokens (currency) | Time Estimate | Time Logged | Urgency (1-5) (number) | Importance (1-5) (number) | Priority | Status
2c24be7 | Further conversations w/ Garri and Sergey from Longevity Science Foundation -> Directed to Mike for collaborations |  |  |  | Keith Comito | 57.477 |  |  | 1h | 1h | 4 | 4 |  | CLOSED [WON]
2c24c8v | Further Ideation calls with Mike s., Audie S., Todd W., Stephanie D., re: collaborations w/ Lifespan, GitCoin, VitaDAO, LabDAO, ResearchHub, etc. and MindMap creation. |  |  |  | Keith Comito | 145.6084 |  |  | 2h | 2h | 4 | 5 |  | CLOSED [WON]
2f7aqmt | Conversations w/ Brent Nally re: integrating LongevityPlan with CureDAO |  |  |  | Keith Comito | 114.954 |  |  | 2h | 2h | 4 | 4 |  | CLOSED [WON]
2cru6bw | Conversation w/ Andrei Doktoroff re: potential HRMNY integrations, and connecting him w/ Mike S |  |  |  | Keith Comito | 143.6925 |  |  | 2h 30m | 2h 30m | 4 | 4 |  | CLOSED [WON]
2ct1650 | Conversations with Fred Zhang from LongevityDAO re: collaborations, and connecting w/ Mike S. |  |  |  | Keith Comito | 114.954 |  |  | 2h | 2h | 4 | 4 |  | CLOSED [WON]
2fjux2p | Conversations with Konstantin and Akshaj from DeathlessDAO and connecting w/ Mike S. re: collaboration |  |  |  | Keith Comito | 114.954 |  |  | 2h | 2h | 4 | 4 |  | CLOSED [WON]
Eli |  |  |  |  | Total: | 691.6399
Task ID | Task Name | Parent ID | Parent Name | Parent URL | Assignee | Bounty (formula) | TX URL (url) | Sent Tokens (currency) | Time Estimate | Time Logged | Urgency (1-5) (number) | Importance (1-5) (number) | Priority | Status
27wwd7f | Fill in your long and short bio fields if it's OK to list you as a contributor |  |  |  | Eli | 21.0749 |  |  | 30m |  | 3 | 4 | URGENT | CLOSED
Andreas Melhede |  |  |  |  | Total: | 21.0749
Task ID | Task Name | Parent ID | Parent Name | Parent URL | Assignee | Bounty (formula) | TX URL (url) | Sent Tokens (currency) | Time Estimate | Time Logged | Urgency (1-5) (number) | Importance (1-5) (number) | Priority | Status
2kc3vbu | Reach out To People To Fill In Their Compensation Prior to using ClickUp |  |  |  | Andreas Melhede | 115.2733 |  |  | 1h 35m | 1h 35m | 4 | 5 | HIGH | CLOSED
2nw2k5h | Compensate people with tokens |  |  |  | Andreas Melhede | 194.6554 |  |  | 2h 7m | 2h 8m | 5 | 5 | URGENT | CLOSED
2x5dkrh | Add to Clickup, make them guests, create onboarding tasks for them, and grant them access to their onboarding tasks | 2x5dkr7 | Bradley Yarrow | https://app.clickup.com/t/2x5dkr7 | Andreas Melhede | 0 | [7 empty] | CLOSED
2r6cxmk | Restructure roles |  |  |  | Andreas Melhede | 395.4418 |  |  | 4h 18m | 4h 18m | 5 | 5 | HIGH | CLOSED
2r6mgdk | Onboarding People & Organizational Work |  |  |  | Andreas Melhede | 427.118 |  |  | 5h 52m | 5h 52m | 4 | 5 | URGENT | CLOSED
2r6mghm | Update Orbit Discord integration |  |  |  | Andreas Melhede | 0 |  |  | 1m |  | 4 | 4 | HIGH | CLOSED
2r6mgpd | Check on deadlines for tasks |  |  |  | Andreas Melhede | 21.4581 |  |  | 14m | 14m | 5 | 5 | URGENT | CLOSED
2rhw2ta | Update Orbit Discord integration |  |  |  | Andreas Melhede | 0 |  |  | 1m | 1m | 4 | 4 | HIGH | CLOSED
2rhw2zv | Onboarding People & Organizational Work |  |  |  | Andreas Melhede | 677.0791 |  |  | 9h 18m | 9h 19m | 4 | 5 | URGENT | CLOSED
2rhw50d | Check on deadlines for tasks |  |  |  | Andreas Melhede | 13.7945 |  |  | 9m | 9m | 5 | 5 | URGENT | CLOSED
2ad5vfd | Ask Saava/R42 About BVI/Malta Incorporation |  |  |  | Andreas Melhede | 56.7106 |  |  | 37m | 38m | 5 | 5 |  | CLOSED
2rj2fwv | Update Orbit Discord integration |  |  |  | Andreas Melhede | 0 |  |  | 1m |  | 4 | 4 | HIGH | CLOSED
2rj2tf6 | Onboarding People & Organizational Work |  |  |  | Andreas Melhede | 365.2344 |  |  | 5h 1m | 5h 2m | 4 | 5 | URGENT | CLOSED
2rj2zdy | Check on deadlines for tasks |  |  |  | Andreas Melhede | 12.2618 |  |  | 8m | 8m | 5 | 5 | URGENT | CLOSED
2rqnju2 | Update Orbit Discord integration |  |  |  | Andreas Melhede | 0 |  |  | 1m |  | 4 | 4 | HIGH | CLOSED
2rqnjxz | Onboarding People & Organizational Work |  |  |  | Andreas Melhede | 459.8799 |  |  | 6h 19m | 6h 19m | 4 | 5 | URGENT | CLOSED
2rqnkah | Check on deadlines for tasks |  |  |  | Andreas Melhede | 22.9908 |  |  | 15m | 15m | 5 | 5 | URGENT | CLOSED
2cdjjv0 | Send 10 $CURE1 Tokens & let them know | 2cdjjuu | Fehim Tabak | https://app.clickup.com/t/2cdjjuu | Andreas Melhede | 0 | [7 empty] | CLOSED
2rqtqb2 | Update Orbit Discord integration |  |  |  | Andreas Melhede | 0 |  |  | 1m |  | 4 | 4 | HIGH | CLOSED
2rqtqqd | Onboarding People & Organizational Work |  |  |  | Andreas Melhede | 738.9626 |  |  | 10h 9m | 10h 10m | 4 | 5 | URGENT | CLOSED
2rqtuh0 | Check on deadlines for tasks |  |  |  | Andreas Melhede | 7.6636 |  |  | 5m |  | 5 | 5 | URGENT | CLOSED
2rxep69 | Update Orbit Discord integration |  |  |  | Andreas Melhede | 0 |  |  | 1m |  | 4 | 4 | HIGH | CLOSED
2rxeq20 | Onboarding People & Organizational Work |  |  |  | Andreas Melhede | 510.8428 |  |  | 7h 1m | 7h 1m | 4 | 5 | URGENT | CLOSED
2rxf4c1 | Check on deadlines for tasks |  |  |  | Andreas Melhede | 4.5982 |  |  | 3m | 4m | 5 | 5 | URGENT | CLOSED
25cwkqu | Schedule SF Meetings |  |  |  | Andreas Melhede | 827.6688 |  |  | 9h | 9h | 5 | 5 | URGENT | CLOSED [WON]
2ydawc8 | Send 10 $CURE1 Tokens & let them know | 2ydawc1 | Jesse Uche | https://app.clickup.com/t/2ydawc1 | Andreas Melhede | 0 | [7 empty] | CLOSED
2ydbrxq | Send 10 $CURE1 Tokens & let them know | 2ydbrxn | James Uche | https://app.clickup.com/t/2ydbrxn | Andreas Melhede | 0 | [7 empty] | CLOSED
295m2pf | Add to Discord Labs | 295m2p8 | Aisha Ahmadi | https://app.clickup.com/t/295m2p8 | Andreas Melhede | 0 | [7 empty] | CLOSED
2t315h8 | Onboarding People & Organizational Work |  |  |  | Andreas Melhede | 448.9592 |  |  | 6h 10m | 6h 14m | 4 | 5 | URGENT | CLOSED
2t315t1 | Update Orbit Discord integration |  |  |  | Andreas Melhede | 0 |  |  | 1m |  | 4 | 4 | HIGH | CLOSED
2t315y1 | Check on deadlines for tasks |  |  |  | Andreas Melhede | 4.5982 |  |  | 3m | 4m | 5 | 5 | URGENT | CLOSED
2x566tj | Add to Discord Labs | 2x566rw | Paul Spiegel | https://app.clickup.com/t/2x566rw | Andreas Melhede | 0 | [7 empty] | CLOSED
2ydd4mt | Send 10 $CURE1 Tokens & let them know | 2ydd4mr | Chino Chinedu | https://app.clickup.com/t/2ydd4mr | Andreas Melhede | 0 | [7 empty] | CLOSED
2kqjyku | Determine The Compensation for the rest of the people prior to using ClickUp |  |  |  | Mike Sinn, Andreas Melhede | 72.8042 |  |  | 2h | 1h | 4 | 5 | HIGH | CLOSED
[5 empty] | Total: | 5377.9953
Ageless Partners
Task ID | Task Name | Parent ID | Parent Name | Parent URL | Assignee | Bounty (formula) | TX URL (url) | Sent Tokens (currency) | Time Estimate | Time Logged | Urgency (1-5) (number) | Importance (1-5) (number) | Priority | Status
2y20yzf | promote curedao |  |  |  | Ageless Partners | 14.0499 |  |  | 20m |  | 4 | 3 |  | CLOSED
2y225hb | Boosting Server & promoting CureDAO on social media |  |  |  | Ageless Partners | 28.7385 |  |  | 30m |  | 4 | 4 |  | CLOSED
2xpga7g | Tracking From 4-26-2022 - 5/15/2022 - Ageless Partners |  |  | https://app.clickup.com/t/2xpga7g |  | 594.3122 |  |  | 14h 6m
[5 empty] | Total: | 637.1006