## Tasks
Mike Sinn & Andreas Melhede
Task ID | Task Name | Parent ID | Parent Name | Parent URL | Assignee | Bounty (formula) | TX URL (url) | Sent Tokens (currency) | Time Estimate | Time Logged | Urgency (1-5) (number) | Importance (1-5) (number) | Priority | Status
25zkymm | Import relevant blog post pages, save local copy, and post on DeWork |  |  |  | Mike Sinn, Andreas Melhede | 364.021 |  |  | 5h | Mike: 4:29:29 & Andreas: 0:58:22 | 4 | 5 | URGENT | CLOSED
Wouter van der Linden |  |  |  |  | Mike Compensation | 302.8655 | Andreas Compensation | 61.1555
Task ID | Task Name | Parent ID | Parent Name | Parent URL | Assignee | Bounty (formula) | TX URL (url) | Sent Tokens (currency) | Time Estimate | Time Logged | Urgency (1-5) (number) | Importance (1-5) (number) | Priority | Status
25mabgc | Add CureDAO Calendar to Google Calendar |  |  |  | Wouter van der Linden | 2.6823 |  |  | 3m |  | 3 | 5 | HIGH | CLOSED
25mabhp | Do this last: How would you improve the onboarding process? |  |  |  | Wouter van der Linden | 14.5608 |  |  | 12m |  | 4 | 5 | HIGH | CLOSED
Vincenzo Domina |  |  |  |  | Total Compensation: | 17.2431
Task ID | Task Name | Parent ID | Parent Name | Parent URL | Assignee | Bounty (formula) | TX URL (url) | Sent Tokens (currency) | Time Estimate | Time Logged | Urgency (1-5) (number) | Importance (1-5) (number) | Priority | Status
25zknfj | Home and Prioritizing your team's tasks |  |  |  | Vincenzo Domina | 2.6823 |  |  | 3m |  | 3 | 5 | HIGH | CLOSED
25zknfb | Save your team time with reusable templates! |  |  |  | Vincenzo Domina | 2.6823 |  |  | 3m |  | 3 | 5 | HIGH | CLOSED
25zknfx | Task Statuses and Priorities |  |  |  | Vincenzo Domina | 2.6823 |  |  | 3m |  | 3 | 5 | HIGH | CLOSED
25zknfq | Add $GCURES to MetaMask |  |  |  | Vincenzo Domina | 11.6231 |  |  | 13m |  | 3 | 5 | HIGH | CLOSED
25zknf8 | Add CureDAO Calendar to Google Calendar |  |  |  | Vincenzo Domina | 0.89409 |  |  | 1m |  | 3 | 5 | HIGH | CLOSED
25zknf6 | Filter and sort your tasks |  |  |  | Vincenzo Domina | 1.3411 |  |  | 3m |  | 2 | 4 | NORMAL | CLOSED
25zknfm | Recurring tasks: this task will restart when closed |  |  |  | Vincenzo Domina | 1.3411 |  |  | 3m |  | 2 | 4 | NORMAL | CLOSED
25zknf5 | Managing ClickUp Notifications |  |  |  | Vincenzo Domina | 1.7882 |  |  | 4m |  | 2 | 4 | NORMAL | CLOSED
25zknf4 | How to make social media posts |  |  |  | Vincenzo Domina | 1.3411 |  |  | 3m |  | 2 | 4 | NORMAL | CLOSED
Mike Sinn |  |  |  |  | Total Compensation: | 26.3756
Task ID | Task Name | Parent ID | Parent Name | Parent URL | Assignee | Bounty (formula) | TX URL (url) | Sent Tokens (currency) | Time Estimate | Time Logged | Urgency (1-5) (number) | Importance (1-5) (number) | Priority | Status
2duhdnh | Create Feedback Page |  |  |  | Mike Sinn | 42.1498 |  |  | 1h | 1h 39m | 3 | 4 | HIGH | COMPLETE
23efcqb | QuantiModo skipped a word in his instructions |  |  |  | Mike Sinn | 72.8042 |  |  | 1h | 1h 28m | 4 | 5 | NORMAL | RESOLVED
2j2nz2j | Share gmail with Sandra Lastpass |  |  |  | Mike Sinn | 7.2804 |  |  | 6m |  | 4 | 5 | LOW | CLOSED
2hbp75u | Draft Whitepaper |  |  |  | Mike Sinn | 91.9632 |  |  |  |  | 5 | 5 |  | CLOSED
2hpzh9v | Create proof-of-concept demo app for data sharing and analysis |  |  |  | Mike Sinn | 364.021 |  |  | 5h |  | 4 | 5 | URGENT | CLOSED
2jkpkua | Sign up for $100K from Google Cloud for Startups |  |  |  | Mike Sinn | 15.3272 |  |  | 1h |  | 1 | 5 | LOW | CLOSED
2nn3y1w | Setup Discord Discourse Integration |  |  |  | Mike Sinn | 6.1309 |  |  | 24m | 11m | 1 | 5 | LOW | CLOSED
2nun1an | Create Collaborator Application Form |  |  |  | Mike Sinn | 42.1498 |  |  | 1h |  | 3 | 4 | NORMAL | CLOSED [WON]
2hwt88e | determine discover | 2hwt889 | Site terminology | https://app.clickup.com/t/2hwt889 | Mike Sinn | 0 | [7 empty] | CLOSED
2pbz0aj | Fix favicons on study searches |  |  |  | Mike Sinn | 3.8318 |  |  | 20m |  | 2 | 2 | NORMAL | CLOSED
2pq918h | Make Build Unnecessary: Handle missing buildInfo.json, ensure navigator is available, pre-compile CSS, etc. |  |  |  | Mike Sinn | 26.8226 |  |  | 30m | 2h 47m | 3 | 5 | HIGH | CLOSED
2px2xym | Fix broken connector images |  |  |  | Mike Sinn | 36.4021 |  |  | 30m |  | 4 | 5 | HIGH | CLOSED
Mark Melnykowycz |  |  |  |  | Total Compensation: | 1011.7485
Task ID | Task Name | Parent ID | Parent Name | Parent URL | Assignee | Bounty (formula) | TX URL (url) | Sent Tokens (currency) | Time Estimate | Time Logged | Urgency (1-5) (number) | Importance (1-5) (number) | Priority | Status
258zc91 | How to make social media posts |  |  |  | Mark Melnykowycz | 2.6823 |  |  | 3m |  | 3 | 5 | NORMAL | CLOSED
258zc8x | How to Use Github |  |  |  | Mark Melnykowycz | 2.6823 |  |  | 3m |  | 3 | 5 | NORMAL | CLOSED
258zc88 | Filter and sort your tasks |  |  |  | Mark Melnykowycz | 2.6823 |  |  | 3m |  | 3 | 5 | NORMAL | CLOSED
258zc8k | Collaborating with tasks |  |  |  | Mark Melnykowycz | 2.6823 |  |  | 3m |  | 3 | 5 | NORMAL | CLOSED
258zc86 | Recurring tasks: this task will restart when closed |  |  |  | Mark Melnykowycz | 2.6823 |  |  | 3m |  | 3 | 5 | NORMAL | CLOSED
258zc8v | Organizing with the Hierarchy |  |  |  | Mark Melnykowycz | 2.6823 |  |  | 3m |  | 3 | 5 | NORMAL | CLOSED
258zc87 | Managing ClickUp Notifications |  |  |  | Mark Melnykowycz | 2.6823 |  |  | 3m |  | 3 | 5 | NORMAL | CLOSED
258zc8f | Weekly Team Goals |  |  |  | Mark Melnykowycz | 2.6823 |  |  | 3m |  | 3 | 5 | NORMAL | CLOSED
258zc8b | Disable Hot Keys for Better Linking to Documents |  |  |  | Mark Melnykowycz | 1.5327 |  |  | 3m |  | 3 | 3 | NORMAL | CLOSED
258zc8y | Custom Fields |  |  |  | Mark Melnykowycz | 2.1075 |  |  | 3m |  | 3 | 4 | NORMAL | CLOSED
258zc8t | Communication with your team in ClickUp |  |  |  | Mark Melnykowycz | 1.5327 |  |  | 3m |  | 3 | 3 | LOW | CLOSED
258zc89 | ClickUp Views |  |  |  | Mark Melnykowycz | 1.5327 |  |  | 3m |  | 3 | 3 | LOW | CLOSED
258zc8w | Dashboards at a high level to measure your team's progress |  |  |  | Mark Melnykowycz | 1.5327 |  |  | 3m |  | 3 | 3 | LOW | CLOSED
258zc8m | This is a subtask | 258zc8k | Collaborating with tasks | https://app.clickup.com/t/258zc8k | Mark Melnykowycz | 0 | [7 empty] | CLOSED
Haneen |  |  |  |  | Total Compensation: | 29.6965
Task ID | Task Name | Parent ID | Parent Name | Parent URL | Assignee | Bounty (formula) | TX URL (url) | Sent Tokens (currency) | Time Estimate | Time Logged | Urgency (1-5) (number) | Importance (1-5) (number) | Priority | Status
25u14f4 | Setting due dates to keep your team on track |  |  |  | Haneen | 7.6636 |  |  | 5m |  | 5 | 5 | HIGH | CLOSED
Andreas Melhede |  |  |  |  | Total Compensation: | 7.6636
Task ID | Task Name | Parent ID | Parent Name | Parent URL | Assignee | Bounty (formula) | TX URL (url) | Sent Tokens (currency) | Time Estimate | Time Logged | Urgency (1-5) (number) | Importance (1-5) (number) | Priority | Status
2gmvp2u | Create Lab Coordinator Forms |  |  |  | Andreas Melhede | 582.4336 |  |  | 8h | 6h 18m | 4 | 5 | URGENT | CLOSED
24c5krv | Create another landing page version |  |  |  | Andreas Melhede | 800.8462 |  |  | 11h | 10h 41m | 4 | 5 | HIGH | CLOSED
2jdz44j | Determine and include benefits and responsibilities of being a lab coordinator, qualifications, expected time commitments, etc | 2gmvp2u | Create Lab Coordinator Forms | https://app.clickup.com/t/2gmvp2u | Andreas Melhede | 0 | [6 empty] | URGENT | CLOSED
2hhg9a6 | Create compensation documentation |  |  |  | Andreas Melhede | 509.6294 |  |  | 7h | 7h 55m | 4 | 5 | URGENT | CLOSED
24c5krw | Go through the landing page one more time | 24c5krv | Create another landing page version | https://app.clickup.com/t/24c5krv | Andreas Melhede | 0 | [7 empty] | CLOSED
25u1kzu | Optimize Onboarding Flow |  |  |  | Andreas Melhede | 109.2063 |  |  | 1h 30m | 1h 28m | 4 | 5 | URGENT | CLOSED
25u46kt | Update the compensation amounts for the onboarding tasks |  |  |  | Andreas Melhede | 36.4021 |  |  | 30m | 32m | 4 | 5 | URGENT | CLOSED
25zmtnk | Re-evaluate tasks' urgency and importance |  |  |  | Andreas Melhede | 72.8042 |  |  | 1h | 33m | 4 | 5 |  | CLOSED
2juqvrj | Send them 10 $CURE1 Tokens | 2juqvr3 | Blair Z | https://app.clickup.com/t/2juqvr3 | Andreas Melhede | 0 | [7 empty] | CLOSED
25zuq7y | Restructure The Onboarding Tasks |  |  |  | Andreas Melhede | 18.201 |  |  | 15m | 7m | 4 | 5 | URGENT | CLOSED
25zw3yz | Ask people to set due dates for their tasks & add some due dates |  |  |  | Andreas Melhede | 127.4073 |  |  | 1h 45m | 1h 43m | 4 | 5 | HIGH | CLOSED
25zw9fq | Add valuable information about what the ClickUp App Can Do for the individual in the onboarding tasks |  |  |  | Andreas Melhede | 14.3693 |  |  | 15m | 13m | 4 | 4 | HIGH | CLOSED
25zwm68 | Send a Discord message to people including the doc linked above about our intentions | 25zw3yz | Ask people to set due dates for their tasks & add some due dates | https://app.clickup.com/t/25zw3yz | Andreas Melhede | 0 | [7 empty] | CLOSED
265ak7m | Add to Mike's based on the priority of his tasks without asking him. | 25zw3yz | Ask people to set due dates for their tasks & add some due dates | https://app.clickup.com/t/25zw3yz | Andreas Melhede | 0 | [7 empty] | CLOSED
2juue66 | Have people submit their pre-ClickUp work estimates to be compensated |  |  |  | Andreas Melhede | 36.4021 |  |  | 30m | 26m | 4 | 5 | NORMAL | CLOSED
265b1mx | Add people's available hours to: https://app.clickup.com/10641228/v/wl/a4quc-13140 | 265b1mv | Onboard People | https://app.clickup.com/t/265b1mv | Andreas Melhede | 0 | [7 empty] | CLOSED
265b1mz | Send them 10 $GCURES Tokens | 265b1mv | Onboard People | https://app.clickup.com/t/265b1mv | Andreas Melhede | 0 | [7 empty] | CLOSED
265cntz | Send them 10 $CURE1 Tokens | 265cntw | Ashleigh Nicole | https://app.clickup.com/t/265cntw | Andreas Melhede | 0 | [7 empty] | CLOSED
2juyga3 | Send them 10 $CURE1 Tokens | 2juyga2 | Shan | https://app.clickup.com/t/2juyga2 | Andreas Melhede | 0 | [7 empty] | CLOSED
2juyga4 | Schedule an onboarding call | 2juyga2 | Shan | https://app.clickup.com/t/2juyga2 | Andreas Melhede | 0 | [7 empty] | CLOSED
265e073 | Add people's available hours to: https://app.clickup.com/10641228/v/wl/a4quc-13140 | 265e072 | Onboard People | https://app.clickup.com/t/265e072 | Andreas Melhede | 0 | [7 empty] | CLOSED
265f30z | Assign "Y" Or "N" to tasks that can be put on Dework |  |  |  | Andreas Melhede | 163.8094 |  |  | 2h 15m | 2h 8m | 4 | 5 | URGENT | CLOSED
26vyqe7 | Send them 10 $CURE1 Tokens | 26vyqe6 | Keith Comito | https://app.clickup.com/t/26vyqe6 | Andreas Melhede | 0 | [7 empty] | CLOSED
26vyqe9 | Invite and add to appropriate GitHub teams | 26vyqe6 | Keith Comito | https://app.clickup.com/t/26vyqe6 | Andreas Melhede | 0 | [7 empty] | CLOSED
2ajjngq | Onboarding feedback |  |  |  | Andreas Melhede | 0 | [6 empty] | NORMAL | CLOSED
265fj9v | Restructure the onboarding meeting |  |  |  | Andreas Melhede | 36.4021 |  |  | 30m | 27m | 4 | 5 | HIGH | CLOSED
265fnwc | Add to Clickup | 26vyqe6 | Keith Comito | https://app.clickup.com/t/26vyqe6 | Andreas Melhede | 0 | [7 empty] | CLOSED
265fjah | Add the agenda to all the event descriptions | 265fj9v | Restructure the onboarding meeting | https://app.clickup.com/t/265fj9v | Andreas Melhede | 0 | [7 empty] | CLOSED
| Onboard People |  |  | https://app.clickup.com/t/265e072 | Andreas Melhede | 252.3879 |  |  | 3h 28m | 3h 27m 35s
| Onboard People |  |  | https://app.clickup.com/t/265b1mv | Andreas Melhede | 709.841 |  |  | 9h 45m | 9h 46m 16s
| Onbard The New People that Filled Out the Form |  |  | https://app.clickup.com/t/2gmv4hh | Andreas Melhede | 115.94
3647.2375
Ageless Partners
Task ID | Task Name | Parent ID | Parent Name | Parent URL | Assignee | Bounty (formula) | TX URL (url) | Sent Tokens (currency) | Time Estimate | Time Logged | Urgency (1-5) (number) | Importance (1-5) (number) | Priority | Status
258w00z | Add $GCURES to MetaMask |  |  |  | Ageless Partners | 13.4113 |  |  | 15m | 1h | 3 | 5 | HIGH | CLOSED
270vp9m | Researched how to add tokens to various blockchains and all the components involved. | 258w00z | Add $GCURES to MetaMask | https://app.clickup.com/t/258w00z | Ageless Partners | 0 | [7 empty] | CLOSED
[5 empty] | Total compensation: | 13.4113