## Tasks
Mike Sinn, Andreas Melhede
Task ID | Task Name | Parent ID | Parent Name | Parent URL | Assignee | Bounty (formula) | TX URL (url) | Sent Tokens (currency) | Time Estimate | Time Logged | Urgency (1-5) (number) | Importance (1-5) (number) | Priority | Status
25u3kef | Add Plugin blog posts to the website |  |  |  | Andreas Melhede, Mike Sinn | 582.4336 |  |  | 8h | 7h 58m | 4 | 5 | URGENT | CLOSED
24vv1gx | Apply for $100k from Arch Grants |  |  |  | Mike Sinn, Andreas Melhede | 1103.5584 |  |  | 12h | 5h 29m | 5 | 5 |  | SENT
Vincenzo Domina
Task ID | Task Name | Parent ID | Parent Name | Parent URL | Assignee | Bounty (formula) | TX URL (url) | Sent Tokens (currency) | Time Estimate | Time Logged | Urgency (1-5) (number) | Importance (1-5) (number) | Priority | Status
2hhh1th | Update README to serve as Litepaper |  |  |  | Vincenzo Domina | 145.6084 |  |  | 2h | 2h | 4 | 5 | HIGH | CLOSED
Tohrnii |  |  |  |  | Total: | 145.6084
Task ID | Task Name | Parent ID | Parent Name | Parent URL | Assignee | Bounty (formula) | TX URL (url) | Sent Tokens (currency) | Time Estimate | Time Logged | Urgency (1-5) (number) | Importance (1-5) (number) | Priority | Status
2kqjd6e | Setting due dates to keep your team on track | 2kqjd6d | Onboarding Task | https://app.clickup.com/t/2kqjd6d | Tohrnii | 4.4704 |  |  | 5m |  | 3 | 5 | URGENT | COMPLETE
2kqjd6g | Home and Prioritizing your team's tasks | 2kqjd6d | Onboarding Task | https://app.clickup.com/t/2kqjd6d | Tohrnii | 2.6823 |  |  | 3m |  | 3 | 5 | HIGH | COMPLETE
2kqjd6j | Task Statuses and Priorities | 2kqjd6d | Onboarding Task | https://app.clickup.com/t/2kqjd6d | Tohrnii | 2.2823 |  |  | 3m |  | 3 | 5 | HIGH | COMPLETE
2kqjd6n | Add $GCURES to MetaMask | 2kqjd6d | Onboarding Task | https://app.clickup.com/t/2kqjd6d | Tohrnii | 8.9409 |  |  | 10m |  | 3 | 5 | HIGH | COMPLETE
Mike Sinn |  |  |  |  | Total: | 18.3759
Task ID | Task Name | Parent ID | Parent Name | Parent URL | Assignee | Bounty (formula) | TX URL (url) | Sent Tokens (currency) | Time Estimate | Time Logged | Urgency (1-5) (number) | Importance (1-5) (number) | Priority | Status
2gugu2v | Privacy Policy Page |  |  |  | Mike Sinn | 72.8042 |  |  | 1h | 25m | 4 | 5 | HIGH | COMPLETE
2hwt88g | Change factors to "factors like foods, drugs, additives and supplements" | 2hwt889 | Site terminology | https://app.clickup.com/t/2hwt889 | Mike Sinn | 0 | [7 empty] | CLOSED
2hwt88b | Find a more universally understood word for "open-source" | 2hwt889 | Site terminology | https://app.clickup.com/t/2hwt889 | Mike Sinn | 0 | [7 empty] | CLOSED
2hwt889 | Site terminology |  |  |  | Mike Sinn | 72.8042 |  |  | 1h |  | 4 | 5 | URGENT | CLOSED
251gr6g | Weekly Planning Meeting (Mike) |  |  |  | Mike Sinn | 298.8804 |  |  | 3h 15m | 3h 15m | 5 | 5 |  | CLOSED
251gr70 | Daily Scrum Meeting (Mike) |  |  |  | Mike Sinn | 218.4126 |  |  | 3h | 3h | 4 | 5 |  | CLOSED
2khnwyg | Add CDP numbers to Discourse proposals and restructure the proposals as needed |  |  |  | Mike Sinn | 36.4021 |  |  | 30m |  | 4 | 5 | HIGH | CLOSED
25cuzbr | Daily Scrum Meeting (Mike) |  |  |  | Mike Sinn | 218.4126 |  |  | 3h |  | 4 | 5 |  | CLOSED
25cuzfq | Daily Scrum Meeting (Mike) |  |  |  | Mike Sinn | 218.4126 |  |  | 3h |  | 4 | 5 |  | CLOSED
2836uwu | Add "Design Lab" members to the "CureDAO Design Team" in Figma | 2836uwn | Ganeshan | https://app.clickup.com/t/2836uwn | Mike Sinn | 4.5982 |  |  | 3m |  | 5 | 5 |  | CLOSED
2836uwq | Schedule an onboarding call | 2836uwn | Ganeshan | https://app.clickup.com/t/2836uwn | Mike Sinn | 7.2804 |  |  | 6m |  | 4 | 5 |  | CLOSED
25jff4u | Daily Scrum Meeting (Mike) |  |  |  | Mike Sinn | 218.4126 |  |  | 3h |  | 4 | 5 |  | CLOSED
27q40dv | Daily Scrum Meeting (Mike) |  |  |  | Mike Sinn | 218.4126 |  |  | 3h |  | 4 | 5 |  | CLOSED
24vv1gx | Apply for $100k from Arch Grants |  |  |  | Mike Sinn, Andreas Melhede | 870.5862 |  |  | 12h | 5h 29m | 5 | 5 |  | SENT
25u3kef | Add Plugin blog posts to the website |  |  |  | Andreas Melhede, Mike Sinn | 145.6084 |  |  | 8h | 7h 58m | 4 | 5 | URGENT | CLOSED
[5 empty] | Total: | 2601.0271
Keith Comito
Task ID | Task Name | Parent ID | Parent Name | Parent URL | Assignee | Bounty (formula) | TX URL (url) | Sent Tokens (currency) | Time Estimate | Time Logged | Urgency (1-5) (number) | Importance (1-5) (number) | Priority | Status
27xfdgg | Ideation calls with Mike, Andreas, etc. re: potential collaborations w/ Lifespan, GitCoin, LabDAO, ResearchHub, etc. |  |  |  | Keith Comito | 459.816 |  |  | 5h | 5h | 5 | 5 |  | CLOSED [WON]
27xfe08 | Identifying opportunities for support: Alliance DAO, Impetus Grants, etc. |  |  |  | Keith Comito | 91.9632 |  |  | 1h | 1h | 5 | 5 |  | CLOSED [WON]
27xfe0j | Communications w/ Qiao W. re: Alliance DAO and potential support / collaborations |  |  |  | Keith Comito | 183.9264 |  |  | 2h | 2h | 5 | 5 |  | CLOSED [WON]
27xfe11 | Communications w/ Audie S. re VitaDAO potential support / collaborations |  |  |  | Keith Comito | 183.9264 |  |  | 2h | 2h | 5 | 5 |  | CLOSED [WON]
Andreas Melhede |  |  |  |  | Total: | 919.632
Task ID | Task Name | Parent ID | Parent Name | Parent URL | Assignee | Bounty (formula) | TX URL (url) | Sent Tokens (currency) | Time Estimate | Time Logged | Urgency (1-5) (number) | Importance (1-5) (number) | Priority | Status
26b23x6 | Compensate people with tokens |  |  |  | Andreas Melhede | 314.2076 |  |  | 3h 25m | 3h 32m | 5 | 5 | URGENT | CLOSED
2khnurb | Update the onboarding tasks to fit a better flow and order |  |  |  | Andreas Melhede | 48.5361 |  |  | 40m | 39m | 4 | 5 | HIGH | CLOSED
2khnvtv | Update the onboarding template when a new person fills out the form |  |  |  | Andreas Melhede | 24.2681 |  |  | 20m | 16m | 4 | 5 | URGENT | CLOSED
251aqud | Schedule an onboarding call | 251aqub | kyle@servingimpact.com | https://app.clickup.com/t/251aqub | Andreas Melhede | 0 | [7 empty] | CLOSED
251aquj | Add to Clickup, make them guests, create onboarding tasks for them, and grant them access to their onboarding tasks | 251aqub | kyle@servingimpact.com | https://app.clickup.com/t/251aqub | Andreas Melhede | 0 | [7 empty] | CLOSED
2c5wyj3 | Add to Discord Labs | 2c5wyhy | Eli | https://app.clickup.com/t/2c5wyhy | Andreas Melhede | 0 | [7 empty] | CLOSED
2khtv0p | Update Orbit Discord integration |  |  |  | Andreas Melhede | 1.2134 |  |  | 1m | 1m | 4 | 5 | HIGH | CLOSED
2khu5mp | Check on deadlines for tasks |  |  |  | Andreas Melhede | 18.3926 |  |  | 12m | 11m | 5 | 5 | URGENT | CLOSED
2khw2vn | Onboarding People & Organizational Work |  |  |  | Andreas Melhede | 339.7529 |  |  | 4h 40m | 4h 41m | 4 | 5 | URGENT | CLOSED
2kqbrtb | Onboarding People & Organizational Work |  |  |  | Andreas Melhede | 445.319 |  |  | 6h 7m | 6h 7m | 4 | 5 | URGENT | CLOSED
2kqby9g | Compensate Taru & Sandra for the work prior to ClickUp |  |  |  | Andreas Melhede | 30.6544 |  |  | 20m | 18m | 5 | 5 | URGENT | CLOSED
2kqc0zc | Check on deadlines for tasks |  |  |  | Andreas Melhede | 18.3926 |  |  | 12m | 10m | 5 | 5 | URGENT | CLOSED
2kqc1gb | Update Orbit Discord integration |  |  |  | Andreas Melhede | 1.2134 |  |  | 1m | 1m | 4 | 5 | HIGH | CLOSED
27xdc9q | Send them 10 $CURE1 Tokens | 27xdc9k | tohrnii | https://app.clickup.com/t/27xdc9k | Andreas Melhede | 0 | [7 empty] | CLOSED
27xdc9v | Schedule an onboarding call | 27xdc9k | tohrnii | https://app.clickup.com/t/27xdc9k | Andreas Melhede | 0 | [7 empty] | CLOSED
27xdca1 | Add to Clickup | 27xdc9k | tohrnii | https://app.clickup.com/t/27xdc9k | Andreas Melhede | 0 | [7 empty] | CLOSED
2kqjd06 | Onboarding People & Organizational Work |  |  |  | Andreas Melhede | 573.9398 |  |  | 7h 53m | 7h 53m | 4 | 5 | URGENT | CLOSED
2kqjp5k | Check on deadlines for tasks |  |  |  | Andreas Melhede | 18.3926 |  |  | 12m | 15m | 5 | 5 | URGENT | CLOSED
2kqjphh | Update Orbit Discord integration |  |  |  | Andreas Melhede | 0.958 |  |  | 1m | 1m | 4 | 4 | HIGH | CLOSED
2kqk12c | Add their weekly available hours here: https://app.clickup.com/10641228/v/wl/a4quc-13140 | 251aqub | kyle@servingimpact.com | https://app.clickup.com/t/251aqub | Andreas Melhede | 0 | [7 empty] | CLOSED
265g1gw | Add Lab Coordinator Forms To The Website |  |  |  | Andreas Melhede | 206.9172 |  |  | 2h 15m | 2h 16m | 5 | 5 | URGENT | CLOSED
2mtqg3c | Add in the copy in the job template posts in Webflow | 265g1gw | Add Lab Coordinator Forms To The Website | https://app.clickup.com/t/265g1gw | Andreas Melhede | 0 | [7 empty] | CLOSED
2mtqgdb | Add links to the forms at the end | 265g1gw | Add Lab Coordinator Forms To The Website | https://app.clickup.com/t/265g1gw | Andreas Melhede | 0 | [7 empty] | CLOSED
2kqjypm | Restructure the compensation structure |  |  |  | Andreas Melhede | 183.9264 |  |  | 2h | 1h 60m | 5 | 5 | URGENT | CLOSED
25190q8 | Create Pre-Genesis Contribution Proposal |  |  |  | Andreas Melhede | 91.9632 |  |  | 1h | 56m | 5 | 5 |  | CLOSED
27cemyh | Initial order of tasks in Onboarding |  |  |  | Andreas Melhede | 0 | [6 empty] | NORMAL | CLOSED
2mtrpyn | Onboarding People & Organizational Work |  |  |  | Andreas Melhede | 643.1038 |  |  | 8h 50m | 8h 50m | 4 | 5 | URGENT | CLOSED
2mtrzdc | Design the job posts career page in Webflow | 265g1gw | Add Lab Coordinator Forms To The Website | https://app.clickup.com/t/265g1gw | Andreas Melhede | 0 | [7 empty] | CLOSED
2836uwp | Send 10 $CURE1 Tokens | 2836uwn | Ganeshan | https://app.clickup.com/t/2836uwn | Andreas Melhede | 0 | [7 empty] | CLOSED
2836uwv | Add to Discord Labs | 2836uwn | Ganeshan | https://app.clickup.com/t/2836uwn | Andreas Melhede | 0 | [7 empty] | CLOSED
2836uww | Add to Clickup, make them guests, create onboarding tasks for them, and grant them access to their onboarding tasks | 2836uwn | Ganeshan | https://app.clickup.com/t/2836uwn | Andreas Melhede | 0 | [7 empty] | CLOSED
2836uwx | Add their weekly available hours here: https://app.clickup.com/10641228/v/wl/a4quc-13140 | 2836uwn | Ganeshan | https://app.clickup.com/t/2836uwn | Andreas Melhede | 0 | [7 empty] | CLOSED
2mtuq2z | Update Orbit Discord integration |  |  |  | Andreas Melhede | 0.958 |  |  | 1m | 1m | 4 | 4 | HIGH | CLOSED
2mtuz1x | Check on deadlines for tasks |  |  |  | Andreas Melhede | 18.3926 |  |  | 12m | 11m | 5 | 5 | URGENT | CLOSED
2mty606 | Create More General Job Application Forms For Each Lab To Put On The Website |  |  |  | Andreas Melhede | 137.9448 |  |  | 1h 30m | 1h 20m | 5 | 5 | URGENT | CLOSED
2mzejwp | Onboarding People & Organizational Work |  |  |  | Andreas Melhede | 370.088 |  |  | 5h 5m | 5h 14m | 4 | 5 | URGENT | CLOSED
2mzeprp | Update Orbit Discord integration |  |  |  | Andreas Melhede | 0.958 |  |  | 1m | 1m | 4 | 4 | HIGH | CLOSED
2mzer4g | Check on deadlines for tasks |  |  |  | Andreas Melhede | 21.4581 |  |  | 14m | 13m | 5 | 5 | URGENT | CLOSED
2mzf0nz | Change PR Lab to Communications lab everywhere |  |  |  | Andreas Melhede | 61.3088 |  |  | 40m | 37m | 5 | 5 | URGENT | CLOSED
25jnn43 | Create or find spreadsheet of places for posting open job/roles/positions | 25ctzyd | Add DAO positions to founder/startup & the organization to DAO sites | https://app.clickup.com/t/25ctzyd | Andreas Melhede | 91.9632 |  |  | 1h | 59m | 5 | 5 | URGENT | CLOSED
2mzn794 | Onboarding People & Organizational Work |  |  |  | Andreas Melhede | 345.82 |  |  | 4h 45m | 4h 50m | 4 | 5 | URGENT | CLOSED
2mzn7bw | Update Orbit Discord integration |  |  |  | Andreas Melhede | 0.958 |  |  | 1m | 1m | 4 | 4 | HIGH | CLOSED
2mzn8a1 | Check on deadlines for tasks |  |  |  | Andreas Melhede | 21.4581 |  |  | 21m | 21m | 5 | 5 | URGENT | CLOSED
2n55rjv | Put up the job posts from https://docs.curedao.org/ on Angel List & on our website |  |  |  | Andreas Melhede | 61.3088 |  |  | 3h | 3h 5m | 5 | 5 | URGENT | CLOSED
2u3y6d3 | Send 10 $CURE1 Tokens & let them know | 2u3y6d2 | Daniel Muraga | https://app.clickup.com/t/2u3y6d2 | Andreas Melhede | 91.9632 | [7 empty] | CLOSED
2n56y7m | Onboarding People & Organizational Work |  |  |  | Andreas Melhede | 345.82 |  |  | 8h 30m | 8h 31m | 4 | 5 | URGENT | CLOSED
2n56zqe | Update Orbit Discord integration |  |  |  | Andreas Melhede | 0.958 |  |  | 1m | 1m | 4 | 4 | HIGH | CLOSED
2n571gw | Check on deadlines for tasks |  |  |  | Andreas Melhede | 22.9908 |  |  | 15m | 12m | 5 | 5 | URGENT | CLOSED
27wupt5 | Remove "Disney Dollar" and any unnecessary detail regarding tokenomics |  |  |  | Andreas Melhede | 13.7945 |  |  | 9m | 9m | 5 | 5 |  | CLOSED
25u3kef | Add Plugin blog posts to the website |  |  |  | Andreas Melhede, Mike Sinn | 436.8252 |  |  | 8h | 7h 58m | 4 | 5 | URGENT | CLOSED
24vv1gx | Apply for $100k from Arch Grants |  |  |  | Mike Sinn, Andreas Melhede | 232.9738 |  |  | 12h | 5h 29m | 5 | 5 |  | SENT
[5 empty] | Total: | 5239.093
Ageless Partners
Task ID | Task Name | Parent ID | Parent Name | Parent URL | Assignee | Bounty (formula) | TX URL (url) | Sent Tokens (currency) | Time Estimate | Time Logged | Urgency (1-5) (number) | Importance (1-5) (number) | Priority | Status
2td6fyj | On boarding Eli |  |  |  | Ageless Partners | 86.2155 |  |  | 1h 30m | 2h | 4 | 4 |  | CLOSED
2trh5w3 | discussions with Lifespan.io, and further discussions with Eli |  |  |  | Ageless Partners | 143.6925 |  |  | 2h 30m |  | 4 | 4 |  | CLOSED
[5 empty] | Total: | 229.908